**SELECTION OF CONSULTANTS**

**REQUEST FOR PROPOSALS**

**RFP No.: NP-REDD-64749-CS-QCBS**

**Selection of Consulting Services for: Preparation of Advanced draft of Benefit Sharing Plan**

**Client: REDD Implementation Center**

**Country: Nepal**

**Project: Nepal REDD Readiness Preparation Program**

**Issued on: 4th April 2019**

**Preface**

This Request for Proposals (“RFP”) has been prepared by the Client and is based on the Standard Request for Proposals (“SRFP”) issued by the World Bank[[1]](#footnote-1) (“the Bank”), dated September 2011.

The SRFP reflects the structure and the provisions of the Master Procurement Document for Selection of Consultants (“Master Document”) prepared by participating Multilateral Development Banks (MDBs), except where specific considerations within the respective institutions have required a change.

# PART I

# Section 1. Letter of Invitation

**RFP No.** 10/18-19 **Grant No:** P125198

*Kathmandu, 4th April 2019*

Dear Mr./Ms.:

Universal Sustainable Development Consultancy (USDC) with Seeport

SMART Pvt. Ltd

Green Era JV with Asian Centre for Development

Practical Solution Pvt. Ltd

Green Governance JV with Youth Alliance for Environment

1. The Government of Nepal has been allocated grant funds (the “Grant”) from the International Development Association (IDA)(the “Bank”)which are administered by the International Development Association (IDA) (the “Bank”) and executed by the *Ministry of Forests and Environment* (“the Client”). The Client intends to apply the funds to eligible payments under the contract for which this Request for Proposals is issued. Payments by the Bank will be made only at the request of the *REDD Implementation Center* and upon approval by the Bank, and will be subject, in all respects, to the terms and conditions of the grant agreement. The grant agreement prohibits a withdrawal from the grant account for the purpose of any payment to persons or entities, or for any import of goods, if such payment or import, to the knowledge of the Bank, is prohibited by a decision of the United Nations Security council taken under Chapter VII of the Charter of the United Nations. No party other than the Client shall derive any rights from the grant agreement or have any claims to the proceeds of the grant*.*

The Client now invites proposals to provide the following consulting services (hereinafter called “Services”): **Preparation of** **Advanced draft Benefit sharing plan**

More details on the Services are provided in the Terms of Reference (Section 7).

1. This Request for Proposals (RFP) has been addressed to the following shortlisted Consultants:
2. Universal Sustainable Development Consultancy (USDC) with Seeport
3. SMART Pvt. Ltd
4. Green Era JV with Asian Centre for Development
5. Practical Solution Pvt. Ltd
6. Green Governance JV with Youth Alliance for Environment
7. It is not permissible to transfer this invitation to any other firm.
8. A firm will be selected under *QCBS* Method procedures and in a Full Technical Proposal (FTP)format as described in this RFP, in accordance with the policies of the Bank detailed in the Consultants’ Guidelines which can be found at the following website: [*www.worldbank.org/procure*](http://www.worldbank.org/procure).
9. The RFP includes the following documents:

Section 1 - Letter of Invitation

Section 2 - Instructions to Consultants and Data Sheet

Section 3 - Technical Proposal *FTP*- Standard Forms

Section 4 - Financial Proposal - Standard Forms

Section 5 –Eligible Countries

Section 6 – Bank’s Policy – Corrupt and Fraudulent Practices

Section 7 - Terms of Reference

Section 8 - Standard Forms of Contract Lump-Sum

1. Please inform us by 14 *April 2019,*in writing at *REDD IC, Babarmahal*, by facsimile *977-1-4215261*, or by E-mail *info@redd.gov.np*

(a) that you have received the Letter of Invitation; and

(b) Whether you intend to submit a proposal alone or intend to enhance your experience by requesting permission to associate with other firm(s) (if permissible under Section 2, Instructions to Consultants (ITC), Data Sheet 14.1.1).

1. Details on the proposal’s submission date, time and address are provided in Clauses17.7and 17.9 of the ITC.

Yours sincerely,

*Radha Wagle*

*Chief, Joint Secretary, REDD IC*

# Section 2. Instructions to Consultants and Data Sheet

# A. General Provisions

|  |  |  |
| --- | --- | --- |
| Definitions | 1. “Affiliate(s)” means an individual or an entity that directly or indirectly controls, is controlled by, or is under common control with the Consultant. 2. “Applicable Guidelines” means the policies of the Bank governing the selection and Contract award process as set forth in this RFP. 3. “Applicable Law” means the laws and any other instruments having the force of law in the Client’s country, or in such other country as may be specified in the **Data Sheet**, as they may be issued and in force from time to time. 4. “Bank” means the International Bank for Reconstruction and Development (IBRD) or the International Development Association (IDA). 5. “Borrower” means the Government, Government agency or other entity that signs the *grant* agreement with the Bank. 6. “Client” means the implementing agency that signs the Contract for the Services with the selected Consultant. 7. “Consultant” means a legally-established professional consulting firm or an entity that may provide or provides the Services to the Client under the Contract. 8. “Contract” means a legally binding written agreement signed between the Client and the Consultant and includes all the attached documents listed in its Clause 1 (the General Conditions of Contract (GCC), the Special Conditions of Contract (SCC), and the Appendices). 9. “Data Sheet” means an integral part of the Instructions to Consultants (ITC) Section 2 that is used to reflect specific country and assignment conditions to supplement, but not to over-write, the provisions of the ITC. 10. “Day” means a calendar day. 11. “Experts” means, collectively, Key Experts, Non-Key Experts, or any other personnel of the Consultant, Sub-consultant or Joint Venture member(s). 12. “Government” means the government of the Client’s country. 13. “Joint Venture (JV)” means an association with or without a legal personality distinct from that of its members, of more than one Consultant where one member has the authority to conduct all business for and on behalf of any and all the members of the JV, and where the members of the JV are jointly and severally liable to the Client for the performance of the Contract. 14. “Key Expert(s)” means an individual professional whose skills, qualifications, knowledge and experience are critical to the performance of the Services under the Contract and whose CV is taken into account in the technical evaluation of the Consultant’s proposal. 15. “ITC” (this Section 2 of the RFP) mean the Instructions to Consultants that provide~~s~~ the shortlisted Consultants with all information needed to prepare their Proposals. 16. “LOI” (this Section 1 of the RFP) means the Letter of Invitation being sent by the Client to the shortlisted Consultants. 17. “Non-Key Expert(s)” means an individual professional provided by the Consultant or its Sub-consultant and who is assigned to perform the Services or any part thereof under the Contract and whose CVs are not evaluated individually. 18. “Proposal” means the Technical Proposal and the Financial Proposal of the Consultant. 19. “RFP” means the Request for Proposals to be prepared by the Client for the selection of Consultants, based on the SRFP. 20. “SRFP” means the Standard Request for Proposals, which must be used by the Client as the basis for the preparation of the RFP. 21. “Services” means the work to be performed by the Consultant pursuant to the Contract. 22. “Sub-consultant” means an entity to whom the Consultant intends to subcontract any part of the Services while remaining responsible to the Client during the performance of the Contract. 23. “TORs” (this Section 7 of the RFP) means the Terms of Reference that explain the objectives, scope of work, activities, and tasks to be performed, respective responsibilities of the Client and the Consultant, and expected results and deliverables of the assignment. | |
| Introduction | * 1. The Client named in the Data Sheet intends to select a Consultant from those listed in the Letter of Invitation, in accordance with the method of selection specified in the Data Sheet.   2. The shortlisted Consultants are invited to submit a Technical Proposal and a Financial Proposal, or a Technical Proposal only, as specified in the Data Sheet, for consulting services required for the assignment named in the Data Sheet. The Proposal will be the basis for negotiating and ultimately signing the Contract with the selected Consultant.   3. The Consultants should familiarize themselves with the local conditions and take them into account in preparing their Proposals, including attending a pre-proposal conference if one is specified in the Data Sheet. Attending any such pre-proposal conference is optional and is at the Consultants’ expense.   4. The Client will timely provide, at no cost to the Consultants, the inputs, relevant project data, and reports required for the preparation of the Consultant’s Proposal as specified in the Data Sheet. | |
| Conflict ofInterest | * 1. The Consultants required to provide professional, objective, and impartial advice, at all times holding the Client’s interests paramount, strictly avoiding conflicts with other assignments or its own corporate interests, and acting without any consideration for future work.   2. The Consultant has an obligation to disclose to the Client any situation of actual or potential conflict that impacts its capacity to serve the best interest of its Client. Failure to disclose such situations may lead to the disqualification of the Consultant or the termination of its Contract and/or sanctions by the Bank.      1. Without limitation on the generality of the foregoing, the Consultant shall not be hired under the circumstances set forth below: | |
| **a. Conflicting activities** | (i) Conflict between consulting activities and procurement of goods, works or non-consulting services:a firm that has been engaged by the Client to provide goods, works, or non-consulting services for a project, or any of its Affiliates, shall be disqualified from providing consulting services resulting from or directly related to those goods, works, or non-consulting services. Conversely, a firm hired to provide consulting services for the preparation or implementation of a project, or any of its Affiliates, shall be disqualified from subsequently providing goods or works or non-consulting services resulting from or directly related to the consulting services for such preparation or implementation. | |
| **b. Conflicting assignments** | (ii) Conflict among consulting assignments: a Consultant (including its Experts and Sub-consultants) or any of its Affiliates shall not be hired for any assignment that, by its nature, may be in conflict with another assignment of the Consultant for the same or for another Client. | |
| **c. Conflicting relationships** | (iii) Relationship with the Client’s staff :a Consultant (including its Experts and Sub-consultants) that has a close business or family relationship with a professional staff of the Borrower (or of the Client, or of implementing agency, or of a recipient of a part of the Bank’s financing)who are directly or indirectly involved in any part of (i) the preparation of the Terms of Reference for the assignment, (ii) the selection process for the Contract, or (iii) the supervision of the Contract, may not be awarded a Contract, unless the conflict stemming from this relationship has been resolved in a manner acceptable to the Bank throughout the selection process and the execution of the Contract. | |
| Unfair Competitive Advantage | * 1. Fairness and transparency in the selection process require that the Consultants or their Affiliates competing for a specific assignment do not derive a competitive advantage from having provided consulting services related to the assignment in question. To that end, the Client shall indicate in the **Data Sheet** and make available to all shortlisted Consultants together with this RFP all information that would in that respect give such Consultant any unfair competitive advantage over competing Consultants. | |
| Corrupt and Fraudulent Practices | 5.1 The Bank requires compliance with its policy in regard to corrupt and fraudulent practices as set forth in Section 6.  5.2 In further pursuance of this policy, Consultant shall permit and shall cause its agents, Experts, Sub-consultants, sub-contractors, services providers, or suppliers to permit the Bank to inspect all accounts, records, and other documents relating to the submission of the Proposal and contract performance (in case of an award), and to have them audited by auditors appointed by the Bank. | |
| Eligibility | * 1. The Bank permits consultants (individuals and firms, including Joint Ventures and their individual members) from all countries to offer consulting services for Bank-financed projects.   2. Furthermore, it is the Consultant’s responsibility to ensure that its Experts, joint venture members, Sub-consultants, agents (declared or not), sub-contractors, service providers, suppliers and/or their employees meet the eligibility requirements as established by the Bank in the Applicable Guidelines.   3. As an exception to the foregoing Clauses 6.1 and 6.2 above: | |
| **a. Sanctions** | * + 1. A firm or an individual sanctioned by the Bank in accordance with the above Clause 5.1 or in accordance with “Anti-Corruption Guidelines” shall be ineligible to be awarded a Bank-financed contract, or to benefit from a Bank-financed contract, financially or otherwise, during such period of time as the Bank shall determine. The list of debarred firms and individuals is available at the electronic address specified in the **Data Sheet**. | |
| **b. Prohibitions** | * + 1. Firms and individuals of a country or goods manufactured in a country may be ineligible if so indicated in Section 5 (Eligible Countries) and:   (a) as a matter of law or official regulations, the Borrower’s country prohibits commercial relations with that country, provided that the Bank is satisfied that such exclusion does not preclude effective competition for the provision of Services required; or  (b) by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s Country prohibits any import of goods from that country or any payments to any country, person, or entity in that country. | |
| **c. Restrictions for Government-owned Enterprises** | 6.3.3Government-owned enterprises or institutions in the Borrower’s country shall be eligible only if they can establish that they (i) are legally and financially autonomous, (ii) operate under commercial law, and (iii) that they are not dependent agencies of the Client  To establish eligibility, the government-owned enterprise or institution should provide all relevant documents  (including its charter) sufficient to demonstrate that it is a legal entity separate from the government; it does not currently receive any substantial subsidies or budget support; it is not obligated to pass on its surplus to the government; it can acquire rights and liabilities, borrow funds, and can be liable for repayment of debts and be declared bankrupt; and it is not competing for a contract to be awarded by the government department or agency which, under the applicable laws or regulations, is its reporting or supervisory authority or has the ability to exercise influence or control over it. | |
| **d. Restrictions for public employees** | 6.3.4 Government officials and civil servants of the Borrower’s country are not eligible to be included as Experts in the Consultant’s Proposal unless such engagement does not conflict with any employment or other laws, regulations, or policies of the Borrower’s country, and they  (i) are on leave of absence without pay, or have resigned or retired;  (ii) are not being hired by the same agency they were working for before going on leave of absence without pay, resigning, or retiring  (in case of resignation or retirement, for a period of at least 6 (six) months, or the period established by statutory provisions applying to civil servants or government employees in the Borrower’s country, whichever is longer. Experts who are employed by the government-owned universities, educational or research institutions are not eligible unless they have been full time employees of their institutions for a year or more prior to being included in Consultant’s Proposal.; and  (iii) their hiring would not create a conflict of interest. | |
| B. Preparation of Proposals | | |
| General Considerations | * 1. In preparing the Proposal, the Consultant is expected to examine the RFP in detail. Material deficiencies in providing the information requested in the RFP may result in rejection of the Proposal. | |
| Cost of Preparation of Proposal | * 1. The Consultant shall bear all costs associated with the preparation and submission of its Proposal, and the Client shall not be responsible or liable for those costs, regardless of the conduct or outcome of the selection process. The Client is not bound to accept any proposal, and reserves the right to annul the selection process at any time prior to Contract award, without thereby incurring any liability to the Consultant. | |
| Language | * 1. The Proposal, as well as all correspondence and documents relating to the Proposal exchanged between the Consultant and the Client, shall be written in the language(s) specified in the **Data Sheet**. | |
| Documents Comprising the Proposal | * 1. The Proposal shall comprise the documents and forms listed in the **Data Sheet**.   2. If specified in the **Data Sheet**, the Consultant shall include a statement of an undertaking of the Consultant to observe, in competing for and executing a contract, the Client country’s laws against fraud and corruption (including bribery).   3. The Consultant shall furnish information on commissions, gratuities, and fees, if any, paid or to be paid to agents or any other party relating to this Proposal and, if awarded, Contract execution, as requested in the Financial Proposal submission form (Section 4). | |
| Only One Proposal | * 1. The Consultant (including the individual members of any Joint Venture) shall submit only one Proposal, either in its own name or as part of a Joint Venture in another Proposal. If a Consultant, including any Joint Venture member, submits or participates in more than one proposal, all such proposals shall be disqualified and rejected. This does not, however, preclude a Sub-consultant, or the Consultant’s staff from participating as Key Experts and Non-Key Experts in more than one Proposal when circumstances justify and if stated in the **Data Sheet**. | |
| Proposal Validity | * 1. **The Data Sheet** indicates the period during which the Consultant’s Proposal must remain valid after the Proposal submission deadline.   2. During this period, the Consultant shall maintain its original Proposal without any change, including the availability of the Key Experts, the proposed rates and the total price.   3. If it is established that any Key Expert nominated in the Consultant’s Proposal was not available at the time of Proposal submission or was included in the Proposal without his/her confirmation, such Proposal shall be disqualified and rejected for further evaluation, and may be subject to sanctions in accordance with Clause 5 of this ITC. | |
| **a. Extension of Validity Period** | * 1. The Client will make its best effort to complete the negotiations within the proposal’s validity period. However, should the need arise, the Client may request, in writing, all Consultants who submitted Proposals prior to the submission deadline to extend the Proposals’ validity.   2. If the Consultant agrees to extend the validity of its Proposal, it shall be done without any change in the original Proposal and with the confirmation of the availability of the Key Experts.   3. The Consultant has the right to refuse to extend the validity of its Proposal in which case such Proposal will not be further evaluated. | |
| **b. Substitution of Key Experts at Validity Extension** | * 1. If any of the Key Experts become unavailable for the extended validity period, the Consultant shall provide a written adequate justification and evidence satisfactory to the Client together with the substitution request. In such case, a replacement Key Expert shall have equal or better qualifications and experience than those of the originally proposed Key Expert. The technical evaluation score, however, will remain to be based on the evaluation of the CV of the original Key Expert.   2. If the Consultant fails to provide a replacement Key Expert with equal or better qualifications, or if the provided reasons for the replacement or justification are unacceptable to the Client, such Proposal will be rejected with the prior Bank’s no objection. | |
| **c. Sub-Contracting** | * 1. The Consultant shall not subcontract the whole of the Services. | |
| Clarification and Amendment of RFP | * 1. The Consultant may request a clarification of any part of the RFP during the period indicated in the **Data Sheet** before the Proposals’ submission deadline. Any request for clarification must be sent in writing, or by standard electronic means, to the Client’s address indicated in the **Data Sheet**. The Client will respond in writing, or by standard electronic means, and will send written copies of the response (including an explanation of the query but without identifying its source) to all shortlisted Consultants. Should the Client deem it necessary to amend the RFP as a result of a clarification, it shall do so following the procedure described below:      1. At any time before the proposal submission deadline, the Client may amend the RFP by issuing an amendment in writing or by standard electronic means. The amendment shall be sent to all shortlisted Consultants and will be binding on them. The shortlisted Consultants shall acknowledge receipt of all amendments in writing.      2. If the amendment is substantial, the Client may extend the proposal submission deadline to give the shortlisted Consultants reasonable time to take an amendment into account in their Proposals.   2. The Consultant may submit a modified Proposal or a modification to any part of it at any time prior to the proposal submission deadline. No modifications to the Technical or Financial Proposal shall be accepted after the deadline. | |
| Preparation of Proposals – Specific Considerations | * 1. While preparing the Proposal, the Consultant must give particular attention to the following:      1. If a shortlisted Consultant considers that it may enhance its expertise for the assignment by associating with other consultants in the form of a Joint Venture or as Sub-consultants, it may do so with either (a) non-shortlisted Consultant(s), or (b) shortlisted Consultants if permitted in the **Data Sheet**. In all such cases a shortlisted Consultant must obtain the written approval of the Client prior to the submission of the Proposal. When associating with non-shortlisted firms in the form of a joint venture or a sub-consultancy, the shortlisted Consultant shall be a lead member. If shortlisted Consultants associate with each other, any of them can be a lead member.      2. The Client may indicate in the **Data Sheet** the estimated Key Experts’ time input (expressed in person-month) or the Client’s estimated total cost of the assignment, but not both. This estimate is indicative and the Proposal shall be based on the Consultant’s own estimates for the same.      3. If stated in the **Data Sheet**, the Consultant shall include in its Proposal at least the same time input (in the same unit as indicated in the **Data Sheet**) of Key Experts, failing which the Financial Proposal will be adjusted for the purpose of comparison of proposals and decision for award in accordance with the procedure in the **Data Sheet**.      4. For assignments under the Fixed-Budget selection method, the estimated Key Experts’ time input is not disclosed. Total available budget, with an indication whether it is inclusive or exclusive of taxes is given in the **Data Sheet**, and the Financial Proposal shall not exceed this budget. | |
| Technical Proposal Format and Content | * 1. The Technical Proposal shall not include any financial information. A Technical Proposal containing material financial information shall be declared non-responsive.   15.1.1 Consultant shall not propose alternative Key Experts. Only one CV shall be submitted for each Key Expert position. Failure to comply with this requirement will make the Proposal non-responsive.   * 1. Depending on the nature of the assignment, the Consultant is required to submit a Full Technical Proposal (FTP), or a Simplified Technical Proposal (STP) as indicated in the **Data Sheet** and using the Standard Forms provided in Section 3 of the RFP. | |
| Financial Proposal | * 1. The Financial Proposal shall be prepared using the Standard Forms provided in Section 4 of the RFP. It shall list all costs associated with the assignment, including (a) remuneration for Key Experts and Non-Key Experts, (b) reimbursable expenses indicated in the **Data Sheet**. | |
| **a. Price Adjustment** | * 1. For assignments with a duration exceeding 18 months, a price adjustment provision for foreign and/or local inflation for remuneration rates applies if so stated in the **Data Sheet**. | |
| **b. Taxes** | * 1. The Consultant and its Sub-consultants and Experts are responsible for meeting all tax liabilities arising out of the Contract unless stated otherwise in the **Data Sheet**. Information on taxes in the Client’s country is provided in the **Data Sheet**. | |
| **c. Currency of Proposal** | * 1. The Consultant may express the price for its Services in the currency or currencies as stated in the **Data Sheet**. If indicated in the **Data Sheet**, the portion of the price representing local cost shall be stated in the national currency. | |
| **d. Currency of Payment** | * 1. Payment under the Contract shall be made in the currency or currencies in which the payment is requested in the Proposal. | |
| C. Submission, Opening and Evaluation | | |
| Submission, Sealing, and Marking of Proposals | | * 1. The Consultant shall submit a signed and complete Proposal comprising the documents and forms in accordance with Clause 10 (Documents Comprising Proposal). The submission can be done by mail or by hand. If specified in the **Data Sheet**, the Consultant has the option of submitting its Proposals electronically.   2. An authorized representative of the Consultant shall sign the original submission letters in the required format for both the Technical Proposal and, if applicable, the Financial Proposal and shall initial all pages of both. The authorization shall be in the form of a written power of attorney attached to the Technical Proposal.      1. A Proposal submitted by a Joint Venture shall be signed by all members so as to be legally binding on all members, or by an authorized representative who has a written power of attorney signed by each member’s authorized representative.   3. Any modifications, revisions, interlineations, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the Proposal.   4. The signed Proposal shall be marked “Original”, and its copies marked “Copy” as appropriate. The number of copies is indicated in the **Data Sheet**. All copies shall be made from the signed original. If there are discrepancies between the original and the copies, the original shall prevail.   5. The original and all the copies of the Technical Proposal shall be placed inside of a sealed envelope clearly marked “**Technical Proposal**”, “[Name of the Assignment]“, reference number, name and address of the Consultant, and with a warning “**Do Not Open until[insert the date and the time of the Technical Proposal submission deadline]**.”   6. Similarly, the original Financial Proposal (if required for the applicable selection method) shall be placed inside of a sealed envelope clearly marked “**Financial Proposal**” followed by the name of the assignment, reference number, name and address of the Consultant, and with a warning “**Do Not Open With The Technical Proposal**.”   7. The sealed envelopes containing the Technical and Financial Proposals shall be placed into one outer envelope and sealed. This outer envelope shall bear the submission address, RFP reference number, the name of the assignment, Consultant’s name and the address, and shall be clearly marked “**Do Not Open Before**[insert the time and date of the submission deadline indicated in the Data Sheet]”.   8. If the envelopes and packages with the Proposal are not sealed and marked as required, the Client will assume no responsibility for the misplacement, loss, or premature opening of the Proposal.   9. The Proposal or its modifications must be sent to the address indicated in the **Data Sheet** and received by the Client no later than the deadline indicated in the **Data Sheet**, or any extension to this deadline. Any Proposal or its modification received by the Client after the deadline shall be declared late and rejected, and promptly returned unopened. |
| Confidentiality | | * 1. From the time the Proposals are opened to the time the Contract is awarded, the Consultant should not contact the Client on any matter related to its Technical and/or Financial Proposal. Information relating to the evaluation of Proposals and award recommendations shall not be disclosed to the Consultants who submitted the Proposals or to any other party not officially concerned with the process, until the publication of the Contract award information.   2. Any attempt by shortlisted Consultants or anyone on behalf of the Consultant to influence improperly the Client in the evaluation of the Proposals or Contract award decisions may result in the rejection of its Proposal, and may be subject to the application of prevailing Bank’s sanctions procedures.   3. Notwithstanding the above provisions, from the time of the Proposals’ opening to the time of Contract award publication, if a Consultant wishes to contact the Client or the Bank on any matter related to the selection process, it should do so only in writing. |
| Opening of Technical Proposals | | * 1. The Client’s evaluation committee shall conduct the opening of the Technical Proposals in the presence of the shortlisted Consultants’ authorized representatives who choose to attend (in person, or online if this option is offered in the **Data Sheet**). The opening date, time and the address are stated in the **Data Sheet**. The envelopes with the Financial Proposal shall remain sealed and shall be securely stored with a reputable public auditor or independent authority until they are opened in accordance with Clause 23 of the ITC.   2. At the opening of the Technical Proposals the following shall be read out: (i) the name and the country of the Consultant or, in case of a Joint Venture, the name of the Joint Venture, the name of the lead member and the names and the countries of all members; (ii) the presence or absence of a duly sealed envelope with the Financial Proposal; (iii) any modifications to the Proposal submitted prior to proposal submission deadline; and (iv) any other information deemed appropriate or as indicated in the **Data Sheet**. |
| Proposals Evaluation | | * 1. Subject to provision of Clause 15.1 of the ITC, the evaluators of the Technical Proposals shall have no access to the Financial Proposals until the technical evaluation is concluded and the Bank issues its “no objection”, if applicable.   2. The Consultant is not permitted to alter or modify its Proposal in any way after the proposal submission deadline except as permitted under Clause 12.7 of this ITC. While evaluating the Proposals, the Client will conduct the evaluation solely on the basis of the submitted Technical and Financial Proposals. |
| Evaluation of Technical Proposals | | * 1. The Client’s evaluation committee shall evaluate the Technical Proposals on the basis of their responsiveness to the Terms of Reference and the RFP, applying the evaluation criteria, sub-criteria, and point system specified in the **Data Sheet**. Each responsive Proposal will be given a technical score. A Proposal shall be rejected at this stage if it does not respond to important aspects of the RFP or if it fails to achieve the minimum technical score indicated in the **Data Sheet**. |
| Financial Proposals for QBS | | 22.1 Following the ranking of the Technical Proposals, when the selection is based on quality only (QBS), the top-ranked Consultant is invited to negotiate the Contract.  22.2 If Financial Proposals were invited together with the Technical Proposals, only the Financial Proposal of the technically top-ranked Consultant is opened by the Client’s evaluation committee. All other Financial Proposals are returned unopened after the Contract negotiations are successfully concluded and the Contract is signed. |
| Public Opening of Financial Proposals (for QCBS, FBS, and LCS methods) | | * 1. After the technical evaluation is completed and the Bank has issued its no objection (if applicable), the Client shall notify those Consultants whose Proposals were considered non-responsive to the RFP and TOR or did not meet the minimum qualifying technical score (and shall provide information relating to the Consultant’s overall technical score, as well as scores obtained for each criterion and sub-criterion) that their Financial Proposals will be returned unopened after completing the selection process and Contract signing. The Client shall simultaneously notify in writing those Consultants that have achieved the minimum overall technical score and inform them of the date, time and location for the opening of the Financial Proposals. The opening date should allow the Consultants sufficient time to make arrangements for attending the opening. The Consultant’s attendance at the opening of the Financial Proposals (in person, or online if such option is indicated in the **Data Sheet**)is optional and is at the Consultant’s choice.   2. The Financial Proposals shall be opened by the Client’s evaluation committee in the presence of the representatives of those Consultants whose proposals have passed the minimum technical score. At the opening, the names of the Consultants, and the overall technical scores, including the break-down by criterion, shall be read aloud. The Financial Proposals will then be inspected to confirm that they have remained sealed and unopened. These Financial Proposals shall be then opened, and the total prices read aloud and recorded. Copies of the record shall be sent to all Consultants who submitted Proposals and to the Bank. |
| Correction of Errors | | 24.1 Activities and items described in the Technical Proposal but not priced in the Financial Proposal, shall be assumed to be included in the prices of other activities or items, and no corrections are made to the Financial Proposal. |
| **a. Time-Based Contracts** | | 24.1.1 If a Time-Based contract form is included in the RFP, the Client’s evaluation committee will (a) correct any computational or arithmetical errors, and (b) adjust the prices if they fail to reflect all inputs included for the respective activities or items in the Technical Proposal. In case of discrepancy between (i) a partial amount (sub-total) and the total amount, or (ii) between the amount derived by multiplication of unit price with quantity and the total price, or (iii) between words and figures, the former will prevail. In case of discrepancy between the Technical and Financial Proposals in indicating quantities of input, the Technical Proposal prevails and the Client’s evaluation committee shall correct the quantification indicated in the Financial Proposal so as to make it consistent with that indicated in the Technical Proposal, apply the relevant unit price included in the Financial Proposal to the corrected quantity, and correct the total Proposal cost. |
| **b. Lump-Sum Contracts** | | 24.2 If a Lump-Sum contract form is included in the RFP, the Consultant is deemed to have included all prices in the Financial Proposal, so neither arithmetical corrections nor price adjustments shall be made. The total price, net of taxes understood as per Clause ITC25 below, specified in the Financial Proposal (Form FIN-1) shall be considered as the offered price. |
| Taxes | | 25.1 The Client’s evaluation of the Consultant’s Financial Proposal shall exclude taxes and duties in the Client’s country in accordance with the instructions in the **Data Sheet**. |
| Conversion to Single Currency | | For the evaluation purposes, prices shall be converted to a single currency using the selling rates of exchange, source and date indicated in the **Data Sheet**. |
| Combined Quality and Cost Evaluation | |  |
| * 1. **Quality- and Cost-Based Selection (QCBS)** | | In the case of QCBS, the total score is calculated by weighting the technical and financial scores and adding them as per the formula and instructions in the **Data Sheet**. The Consultant achieving the highest combined technical and financial score will be invited for negotiations. |
| **b. Fixed-Budget Selection(FBS)** | | In the case of FBS, those Proposals that exceed the budget indicated in Clause14.1.4 of the **Data Sheet** shall be rejected.  The Client will select the Consultant that submitted the highest-ranked Technical Proposal that does not exceed the budget indicated in the RFP, and invite such Consultant to negotiate the Contract. |
| **c. Least-Cost Selection** | | In the case of Least-Cost Selection (LCS), the Client will select the Consultant with the lowest evaluated total price among those consultants that achieved the minimum technical score, and invite such Consultant to negotiate the Contract. |
| D. Negotiations and Award | | |
| Negotiations | | The negotiations will be held at the date and address indicated in the **Data Sheet** with the Consultant’s representative(s) who must have written power of attorney to negotiate and sign a Contract on behalf of the Consultant.  The Client shall prepare minutes of negotiations that are signed by the Client and the Consultant’s authorized representative. |
| **a. Availability of Key Experts** | | The invited Consultant shall confirm the availability of all Key Experts included in the Proposal as a pre-requisite to the negotiations, or, if applicable, a replacement in accordance with Clause 12 of the ITC. Failure to confirm the Key Experts’ availability may result in the rejection of the Consultant’s Proposal and the Client proceeding to negotiate the Contract with the next-ranked Consultant.  Notwithstanding the above, the substitution of Key Experts at the negotiations may be considered if due solely to circumstances outside the reasonable control of and not foreseeable by the Consultant, including but not limited to death or medical incapacity. In such case, the Consultant shall offer a substitute Key Expert within the period of time specified in the letter of invitation to negotiate the Contract, who shall have equivalent or better qualifications and experience than the original candidate. |
| **b. Technical negotiations** | | The negotiations include discussions of the Terms of Reference (TORs), the proposed methodology, the Client’s inputs, the special conditions of the Contract, and finalizing the “Description of Services” part of the Contract. These discussions shall not substantially alter the original scope of services under the TOR or the terms of the contract, lest the quality of the final product, its price, or the relevance of the initial evaluation be affected. |
| **c. Financial negotiations** | | The negotiations include the clarification of the Consultant’s tax liability in the Client’s country and how it should be reflected in the Contract.  If the selection method included cost as a factor in the evaluation, the total price stated in the Financial Proposal for a Lump-Sum contract shall not be negotiated.  In the case of a Time-Based contract, unit rates negotiations shall not take place, except when the offered Key Experts and Non-Key Experts’ remuneration rates are much higher than the typically charged rates by consultants in similar contracts. In such case, the Client may ask for clarifications and, if the fees are very high, ask to change the rates after consultation with the Bank.  The format for (i) providing information on remuneration rates in the case of Quality Based Selection; and (ii) clarifying remuneration rates’ structure under Clause 28.8 above, is provided in Appendix A to the Financial Form FIN-3: Financial Negotiations – Breakdown of Remuneration Rates. |
| Conclusion of Negotiations | | Thenegotiations are concluded with a review of the finalized draft Contract, which then shall be initialed by the Client and the Consultant’s authorized representative.  If the negotiations fail, the Client shall inform the Consultant in writing of all pending issues and disagreements and provide a final opportunity to the Consultant to respond. If disagreement persists, the Client shall terminate the negotiations informing the Consultant of the reasons for doing so. After having obtained the Bank’s no objection, the Client will invite the next-ranked Consultant to negotiate a Contract. Once the Client commences negotiations with the next-ranked Consultant, the Client shall not reopen the earlier negotiations. |
| Award of Contract | | After completing the negotiations the Client shall obtain the Bank’s no objection to the negotiated draft Contract, if applicable; sign the Contract; publish the award information as per the instructions in the **Data Sheet**; and promptly notify the other shortlisted Consultants.  The Consultant is expected to commence the assignment on the date and at the location specified in the **Data Sheet**. |

Instructions to Consultants

# E. Data Sheet

|  |  |  |
| --- | --- | --- |
| 1. **General** | | |
| **ITC Clause**  **Reference** |  | |
| **1 (c)** | *Nepal* | |
| **2.1** | **Name of the Client: REDD Implementation Center**    **Method of selection**: QCBS as per **Applicable Guidelines:** Selection and Employment of Consultants under IBRD Loans and IDA Credits &Grants by World Bank Borrowers, dated January 2011available on www.worldbank.org/procure | |
| **2.2** | **Financial Proposal to be submitted together with Technical Proposal**:  Yes  **The name of the assignment is**: **Preparation of** **Advanced Draft of Benefit Sharing Plan** | |
| **2.3** | **A pre-proposal conference will be held**: No  Date of pre-proposal conference: NA  Address: REDD IC, Babarmahal  Telephone: 977-1-4239126 Facsimile: 977-1-4215261  E-mail:  Contact person/conference coordinator : | |
| **2.4** | **The Client will provide the following inputs, project data, reports, etc. to facilitate the preparation of the Proposals**:  *[list or state “N/A” if none]* | |
| **4.1** | *NA* | |
| **6.3.1** | **A list of debarred firms and individuals is available at the Bank’s external website***:* [www.worldbank.org/debarr](http://www.worldbank.org/debarr) | |
| **B. Preparation of Proposals** | | |
| **9.1** | **This RFP has been issued in the English language.**  **Proposals shall be submitted in English language.**  **All correspondence exchange shall be in English language.** | |
| **10.1** | **The Proposal shall comprise the following**:  **For FULL TECHNICAL PROPOSAL (FTP):**  **1st Inner Envelope with the Technical Proposal:**   * + - * 1. Power of Attorney to sign the Proposal         2. TECH-1         3. TECH-2         4. TECH-3         5. TECH-4         6. TECH-5         7. TECH-6   **2d Inner Envelope with the Financial Proposal:**  (1) FIN-1  (2) FIN-2  (3) FIN-3  (4) FIN-4  (5)Statement of Undertaking (if required under Data Sheet 10.2 below) | |
| **10.2** | **Statement of Undertaking is required**  No | |
| **11.1** | **Participation of Sub-consultants, Key Experts and Non-Key Experts in more than one Proposal is permissible**  No | |
| **12.1** | **Proposals must remain valid for** *90* calendar days after the proposal submission deadline (i.e., until: *1July 2019)* | |
| **13.1** | **Clarifications may be requested no later than** *10* **days prior to the submission deadline.**  The contact information for requesting clarifications is: REDD Implementation Center, Babarmahal  Facsimile: 977-1-4215261 E-mail: info@redd.gov.np | |
| **14.1.1** | **Shortlisted Consultants may associate with**  **(a) non-shortlisted consultant(s):** Yes | |
| **14.1.2**  (do not use for Fixed Budget method) | **Estimated input of Key Experts’ time-input: 8 person-months.** | |
| **14.1.3**  for time-based contracts only | *“Not applicable”* | |
| **14.1.4 and 27.2**  use for Fixed Budget method | **NA** | |
| **15.2** | The format of the Technical Proposal to be submitted is:  FTP  Submission of the Technical Proposal in a wrong format may lead to the Proposal being deemed non-responsive to the RFP requirements. | |
| **16.1** | *(1) a per diem allowance, including hotel, for experts for every day of absence from the home office for the purposes of the Services;*  *(2) cost of travel by the most appropriate means of transport and the most direct practicable route;*  *(3) cost of office accommodation, including overheads and back-stop support;*  *(4) communications costs;*  *(6) cost of reports production (including printing) and delivering to the Client;* |
| **16.2** | **A price adjustment provision applies to remuneration rates:**  No |
| **16.3** | “**Information on the Consultant’s tax obligations in the Client’s country can be found in** “www.ird.gov.np” |
| **16.4** | **The Financial Proposal shall be stated in the following currencies:**  Consultant may express the price for their Services in Nepalese Rupees only.  Nepalese. |
| **C. Submission, Opening and Evaluation** | |
| **17.1** | **The Consultants *“*shall not*”* have the option of submitting their Proposals electronically.** |
| **17.4** | **The Consultant must submit:**  (a) **Technical Proposal:** one (1) original and one copy;  (b) **Financial Proposal:** one (1) original. |
| **17.7 and 17.9** | **The Proposals must be submitted no later than:**  **Date : 5 May 2019**  **Time***, “12:00 noon”*    **The Proposal submission address is: REDD Implementation Center, Babarmahal** |
| **19.1** | **An online option of the opening of the Technical Proposals is offered:**  No  TP Opening:  **Date**:5 May 2019  **Time:***“1400 hours or 2.00PM”* |
| **19.2** | **In addition, the following information will be read aloud at the opening of the Technical Proposals :** NA |
| **21.1**  (for FTP) | Criteria, sub-criteria, and point system for the evaluation of the Full Technical Proposals:  Points  (i) **Specific experience of the Consultant (as a firm) relevant to the Assignment:** 0  (ii) **Adequacy and quality of the proposed methodology, and work plan in responding to the Terms of Reference (TORs):** *40*  *{Notes to Consultant: the Client will assess whether the proposed methodology is clear, responds to the TORs, work plan is realistic and implementable; overall team composition is balanced and has an appropriate skills mix; and the work plan has right input of Experts}*    (iii) **Key Experts’ qualifications and competence for the Assignment:**  *{Notes to Consultant: each position number corresponds to the same for the Key Experts in Form TECH-6 to be prepared by the Consultant}*   1. *Position K-1: Team Leader 16 Points* 2. *Position K-1: REDD+ Expert 12 Points* 3. *Position K-1: Legal Expert 12 Points* 4. *Position K-1: Gender Expert 10 Points* 5. *Position K-1: Social Inclusion Expert 10 Points*     **Total points for criterion (iii):** *60*  The number of points to be assigned to each of the above positions shall be determined considering the following three sub-criteria and relevant percentage weights:  1) General qualifications(general education, training, and experience): *20 %*  2) Adequacy for the Assignment(relevant education, training, experience in the sector/similar assignments)*: 80%*  3) Relevant experience in the region (working level fluency in local language(s)/knowledge of local culture or administrative system, government organization, etc.):  Total weight: 100%  **Total points for the three criteria*:* 100**  **the minimum technical score (St) required to pass is:** *70* |
| **21.1**  [for STP] | *NA* |
| **23.1** | **An online option of the opening of the Financial Proposals is offered:** No |
| **25.1** | For the purpose of the evaluation, the Client will exclude: (a) all local identifiable indirect taxes such as sales tax, excise tax, VAT, or similar taxes levied on the contract’s invoices; and (b) all additional local indirect tax on the remuneration of services rendered by non-resident experts in the Client’s country. If a Contract is awarded, at Contract negotiations, all such taxes will be discussed, finalized (using the itemized list as a guidance but not limiting to it) and added to the Contract amount as a separate line, also indicating which taxes shall be paid by the Consultant and which taxes are withheld and paid by the Client on behalf of the Consultant. |
| **26.1** | **The single currency for the conversion of all prices expressed in various currencies into a single one is:** Nepalese Rupees  **The official source of the selling (exchange) rate is**: NA  **The date of the exchange rate is: NA** |
| **27.1**  **(QCBS only)** | **The lowest evaluated Financial Proposal (Fm) is given the maximum financial score (Sf) of 100.**  **The formula for determining the financial scores (Sf) of all other Proposals is calculated as following:**  Sf = 100 x Fm/ F, in which “Sf” is the financial score, “Fm” is the lowest price, and “F” the price of the proposal under consideration.  *[or replace with another inversely proportional formula acceptable to the Bank]*  **The weights given to the Technical (T) and Financial (P) Proposals are**:  **T** = 80% and  **P** = 20%  Proposals are ranked according to their combined technical (St) and financial (Sf) scores using the weights (T = the weight given to the Technical Proposal; P = the weight given to the Financial Proposal; T + P = 1) as following: S = St x T% + Sf x P%. |
|  | **D. Negotiations and Award** |
| **28.1** | **Expected date and address for contract negotiations:**  **Date**: 18 June 2019  **Address:** REDD IC, Babarmahal |
| **30.1** | **The publication of the contract award information following the completion of the contract negotiations and contract signing will be done as following: www.redd.gov.np**  The publication will be done within *15***days after the contract signing.** |
| **30.2** | **Expected date for the commencement of the Services:**  **Date**: 16 July 2019**at**: Related places |

# Section 3. Technical Proposal – Standard Forms

{Notes to Consultant shown in brackets { }throughout Section 3 provide guidance to the Consultant to prepare the Technical Proposal; they should not appear on the Proposals to be submitted.}

###### Checklist of Required Forms

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Required for FTP or STP  (√) | | FORM | DESCRIPTION | *Page Limit* |
| FTP | STP |  |  |  |
| √ | √ | TECH-1 | Technical Proposal Submission Form. |  |
| “√ “ If applicable | | TECH-1 Attachment | If the Proposal is submitted by a joint venture, attach a letter of intent or a copy of an existing agreement. |  |
| “√” If applicable | | Power of Attorney | No pre-set format/form. In the case of a Joint Venture, several are required: a power of attorney for the authorized representative of each JV member, and a power of attorney for the representative of the lead member to represent all JV members |  |
| √ |  | TECH-2 | Consultant’s Organization and Experience. |  |
| √ |  | TECH-2A | A. Consultant’s Organization |  |
| √ |  | TECH-2B | B. Consultant’s Experience |  |
| √ |  | TECH-3 | Comments or Suggestions on the Terms of Reference and on Counterpart Staff and Facilities to be provided by the Client. |  |
| √ |  | TECH-3A | A. On the Terms of Reference |  |
| √ |  | TECH-3B | B. On the Counterpart Staff and Facilities |  |
| √ | √ | TECH-4 | Description of the Approach, Methodology, and Work Plan for Performing the Assignment |  |
| √ | √ | TECH-5 | Work Schedule and Planning for Deliverables |  |
| √ | √ | TECH-6 | Team Composition, Key Experts Inputs, and attached Curriculum Vitae (CV) |  |

**All pages of the original Technical and Financial Proposal shall be initialled by the same authorized representative of the Consultant who signs the Proposal.**

###### Form TECH-1

**Technical Proposal Submission Form**

{Location, Date}

To: *[Name and address of Client]*

Dear Sirs:

We, the undersigned, offer to provide the consulting services for *[Insert title of assignment]* in accordance with your Request for Proposals dated *[Insert Date]* and our Proposal. *[Select appropriate wording depending on the selection method stated in the RFP:* “We are hereby submitting our Proposal, which includes this Technical Proposal and a FinancialProposal sealed ina separate envelope” *or, if only a Technical Proposal is invited* “We hereby are submitting our Proposal, which includes this Technical Proposal only in a sealed envelope.*”].*

{If the Consultant is a joint venture, insert the following*:* We are submitting our Proposal a joint venture with: {Insert a list with full name and the legal address of each member, and indicate the lead member}.We have attached a copy {insert: “of our letter of intent to form a joint venture” or, if a JV is already formed, “of the JV agreement”} signed by every participating member, which details the likely legal structure of and the confirmation of joint and severable liability of the members of the said joint venture.

{OR

If the Consultant’s Proposal includes Sub-consultants, insert the following: We are submitting our Proposal with the following firms as Sub-consultants: {Insert a list with full name and address of each Sub-consultant.}

We hereby declare that:

(a) All the information and statements made in this Proposal are true and we accept that any misinterpretation or misrepresentation contained in this Proposal may lead to our disqualification by the Client and/or may be sanctioned by the Bank.

(b) Our Proposal shall be valid and remain binding upon us for the period of time specified in the Data Sheet, Clause 12.1.

(c) We have no conflict of interest in accordance with ITC 3.

(d) We meet the eligibility requirements as stated in ITC 6, and we confirm our understanding of our obligation to abide by the Bank’s policy in regard to corrupt and fraudulent practices as per ITC 5*.*

(e) We, along with any of our sub-consultants, subcontractors, suppliers, or service providers for any part of the contract, are not subject to, and not controlled by any entity or individual that is subject to, a temporary suspension or a debarment imposed by a member of the World Bank Group or a debarment imposed by the World Bank Group in accordance with the Agreement for Mutual Enforcement of Debarment Decisions between the World Bank and other development banks. Further, we are not ineligible under the Employer’s country laws or official regulations or pursuant to a decision of the United Nations Security Council;

(f) *[Note to Client: Only if required in ITC10.2 (Data Sheet 10.2), include the following:* In competing for (and, if the award is made to us, in executing) the Contract, we undertake to observe the laws against fraud and corruption, including bribery, in force in the country of the Client.*]*

(g) Except as stated in the Data Sheet, Clause 12.1, we undertake to negotiate a Contract on the basis of the proposed Key Experts. We accept that the substitution of Key Experts for reasons other than those stated in ITC Clause 12 and ITC Clause 28.4 may lead to the termination of Contract negotiations.

(h) Our Proposal is binding upon us and subject to any modifications resulting from the Contract negotiations.

We undertake, if our Proposal is accepted and the Contract is signed, to initiate the Services related to the assignment no later than the date indicated in Clause 30.2 of the Data Sheet.

We understand that the Client is not bound to accept any Proposal that the Client receives.

We remain,

Yours sincerely,

Authorized Signature {In full and initials}:

Name and Title of Signatory:

Name of Consultant (company’s name or JV’s name):

In the capacity of:

Address:

Contact information (phone and e-mail):

{For a joint venture, either all members shall sign or only the lead member, in which case the power of attorney to sign on behalf of all members shall be attached}

Form TECH-2**(for Full Technical Proposal Only)**

**Consultant’s Organization and Experience**

Form TECH-2: a brief description of the Consultant’s organization and an outline of the recent experience of the Consultant that is most relevant to the assignment. In the case of a joint venture, information on similar assignments shall be provided for each partner. For each assignment, the outline should indicate the names of the Consultant’s Key Experts and Sub-consultants who participated, the duration of the assignment, the contract amount (total and, if it was done in a form of a joint venture or a sub-consultancy, the amount paid to the Consultant), and the Consultant’s role/involvement.

**A - Consultant’s Organization**

1. Provide here a brief description of the background and organization of your company, and – in case of a joint venture – of each member for this assignment.

2. Include organizational chart, a list of Board of Directors, and beneficial ownership

**B - Consultant’s Experience**

1. List only previous similar assignments successfully completed in the last*[*.....*]*years.

2. List only those assignments for which the Consultant was legally contracted by the Client as a company or was one of the joint venture partners. Assignments completed by the Consultant’s individual experts working privately or through other consulting firms cannot be claimed as the relevant experience of the Consultant, or that of the Consultant’s partners or sub-consultants, but can be claimed by the Experts themselves in their CVs. The Consultant should be prepared to substantiate the claimed experience by presenting copies of relevant documents and references if so requested by the Client.

| **Duration** | **Assignment name/& brief description of main deliverables/outputs** | **Name of Client & Country of Assignment** | **Approx. Contract value (in US$ equivalent)/ Amount paid to your firm** | **Role on the Assignment** |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |
| {e.g., Jan.2009– Apr.2010} | {e.g., “Improvement quality of...............”: designed master plan for rationalization of ........; } | {e.g., Ministry of ......, country} | {e.g., US$1 mill/US$0.5 mill} | {e.g., Lead partner in a JV A&B&C} |
|  |  |  |  |  |
| {e.g., Jan-May 2008} | {e.g., “Support to sub-national government.....” : drafted secondary level regulations on..............} | {e.g., municipality of........., country} | {e.g., US$0.2 mil/US$0.2 mil} | {e.g., sole Consultant} |
|  |  |  |  |  |

Form TECH-3 **(for Full Technical Proposal)**

**Comments and Suggestions on the Terms of Reference, Counterpart Staff, and Facilities to be Provided by the Client**

Form TECH-3: comments and suggestions on the Terms of Reference that could improve the quality/effectiveness of the assignment; and on requirements for counterpart staff and facilities, which are provided by the Client, including: administrative support, office space, local transportation, equipment, data, etc.

**A - On the Terms of Reference**

{improvements to the Terms of Reference, if any}

**B - On Counterpart Staff and Facilities**

{comments on counterpart staff and facilities to be provided by the Client. For example, administrative support, office space, local transportation, equipment, data, background reports, etc., if any}

Form TECH-4 **(for Full Technical Proposal Only)**

**Description of Approach, Methodology, and Work Plan in Responding to the Terms of Reference**

Form TECH-4: a description of the approach, methodology and work plan for performing the assignment, including a detailed description of the proposed methodology and staffing for training, if the Terms of Reference specify training as a specific component of the assignment.

{Suggested structure of your Technical Proposal (in FTP format):

1. Technical Approach and Methodology
2. Work Plan
3. Organization and Staffing}

a) ***Technical Approach and Methodology.***{Please explain your understanding of the objectives of the assignment as outlined in the Terms of Reference (TORs), the technical approach, and the methodology you would adopt for implementing the tasks to deliver the expected output(s), and the degree of detail of such output. Please do not repeat/copy the TORs in here.}

b) ***Work Plan.***{Please outline the plan for the implementation of the main activities/tasks of the assignment, their content and duration, phasing and interrelations, milestones (including interim approvals by the Client), and tentative delivery dates of the reports. The proposed work plan should be consistent with the technical approach and methodology, showing your understanding of the TOR and ability to translate them into a feasible working plan. A list of the final documents (including reports) to be delivered as final output(s) should be included here. The work plan should be consistent with the Work Schedule Form.}

c) ***Organization and Staffing.***{Please describe the structure and composition of your team, including the list of the Key Experts, Non-Key Experts and relevant technical and administrative support staff.}

Form TECH-4 **(for Simplified Technical Proposal Only)**

**Description of Approach, Methodology, and Work Plan for Performing the Assignment**

Form TECH-4: a description of the approach, methodology, and work plan for performing the assignment, including a detailed description of the proposed methodology and staffing for training, if the Terms of Reference specify training as a specific component of the assignment.

{Suggested structure of your Technical Proposal}

*a)* ***Technical Approach, Methodology, and Organization of the Consultant’s team****.* {Please explain your understanding of the objectives of the assignment as outlined in the Terms of Reference (TOR), the technical approach, and the methodology you would adopt for implementing the tasks to deliver the expected output(s); the degree of detail of such output; and describe the structure and composition of your team. Please do not repeat/copy the TORs in here.}

*b)* ***Work Plan and Staffing***. {Please outline the plan for the implementation of the main activities/tasks of the assignment, their content and duration, phasing and interrelations, milestones (including interim approvals by the Client), and tentative delivery dates of the reports. The proposed work plan should be consistent with the technical approach and methodology, showing understanding of the TOR and ability to translate them into a feasible working plan and work schedule showing the assigned tasks for each expert. A list of the final documents (including reports) to be delivered as final output(s) should be included here. The work plan should be consistent with the Work Schedule Form.}

*c)* ***Comments (on the TOR and on counterpart staff and facilities)***

{Your suggestions should be concise and to the point, and incorporated in your Proposal. Please also include comments, if any, on counterpart staff and facilities to be provided by the Client. For example, administrative support, office space, local transportation, equipment, data, background reports, etc.}

Form TECH-5**(for FTP and STP)**

**Work Schedule and planning for deliverables**

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **N°** | **Deliverables** 1 **(D-..)** | **Months** | | | | | | | | | | | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **.....** | **n** | **TOTAL** |
| **D-1** | {e.g., Deliverable #1: Report A |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1) data collection |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2) drafting |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3) inception report |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4) incorporating comments |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5) ......................................... |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6) delivery of final report to Client} |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **D-2** | {e.g., Deliverable #2:...............} |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **n** |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1 List the deliverables with the breakdown for activities required to produce them and other benchmarks such as the Client’s approvals. For phased assignments, indicate the activities, delivery of reports, and benchmarks separately for each phase.

2 Duration of activities shall be indicated in a form of a bar chart.

3. Include a legend, if necessary, to help read the chart.

Form TECH-6**(for FTP and STP)**

**Team Composition, Assignment, and Key Experts’ inputs**

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **N°** | **Name** | **Expert’s input (in person/month) per each Deliverable (listed in TECH-5)** | | | | | | | | | | | | | **Total time-input**  **(in Months)** | | |
| **Position** |  | **D-1** |  | **D-2** |  | **D-3** | **........** |  | **D-...** |  |  |  | **Home** | **Field** | **Total** |
| **KEY EXPERTS** | | | |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| K-1 | {e.g., Mr. Abbbb} | [Team Leader] | [*Home]* | [2 month] |  | [1.0] |  | [1.0] |  |  |  |  |  |  |  |  |  |
| [*Field*] | [0.5 m] |  | [2.5] |  | [0] |  |  |  |  |  |  |  |  |
| K-2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| K-3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| n |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | **Subtotal** | | | |  |  |  |
| **NON-KEY EXPERTS** | |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N-1 |  |  | [*Home*] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [*Field*] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N-2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| n |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | **Subtotal** | | | |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | **Total** | | | |  |  |  |

1 For Key Experts, the input should be indicated individually for the same positions as required under the Data Sheet ITC21.1.

2 Months are counted from the start of the assignment/mobilization. One (1) month equals twenty two (22)working (billable) days. One working (billable) day shall be not less than eight (8) working (billable) hours.

3 “Home” means work in the office in the expert’s country of residence. “Field” work means work carried out in the Client’s country or any other country outside the expert’s country of residence.

Full time input

Part time input

**Form TECH-6**

**(Continued)**

**CURRICULUM VITAE (CV)**

|  |  |
| --- | --- |
| **Position Title and No.** | {e.g., K-1, TEAM LEADER} |
| **Name of Expert:** | {Insert full name} |
| **Date of Birth:** | {day/month/year} |
| **Country of Citizenship/Residence** |  |

**Education:** {List college/university or other specialized education, giving names of educational institutions, dates attended, degree(s)/diploma(s) obtained}

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**Employment record relevant to the assignment:** {Starting with present position, list in reverse order. Please provide dates, name of employing organization, titles of positions held, types of activities performed and location of the assignment, and contact information of previous clients and employing organization(s) who can be contacted for references. Past employment that is not relevant to the assignment does not need to be included.}

|  |  |  |  |
| --- | --- | --- | --- |
| **Period** | **Employing organization and your title/position. Contact infor for references** | **Country** | **Summary of activities performed relevant to the Assignment** |
| [e.g., May 2005-present] | [e.g., Ministry of ……, advisor/consultant to…  For references: Tel…………/e-mail……; Mr. deputy minister] |  |  |
|  |  |  |  |
|  |  |  |  |

**Membership in Professional Associations and Publications: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**Language Skills (indicate only languages in which you can work): \_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**Adequacy for the Assignment:**

|  |  |
| --- | --- |
| **Detailed Tasks Assigned on Consultant’s Team of Experts:** | **Reference to Prior Work/Assignments that Best Illustrates Capability to Handle the Assigned Tasks** |
| **{List all deliverables/tasks as in TECH- 5 in which the Expert will be involved)** |  |
|  |  |
|  |  |

**Expert’s contact information:** (e-mail…………………., phone……………)

Certification:

I, the undersigned, certify that to the best of my knowledge and belief, this CV correctly describes myself, my qualifications, and my experience, and I am available to undertake the assignment in case of an award. I understand that any misstatement or misrepresentation described herein may lead to my disqualification or dismissal by the Client, and/or sanctions by the Bank.

{day/month/year}

Name of Expert Signature Date

{day/month/year}

Name of authorized Signature Date

Representative of the Consultant

(the same who signs the Proposal)

# Section 4. Financial Proposal - Standard Forms

{*Notes to Consultant*s hown in brackets { } provide guidance to the Consultant to prepare the Financial Proposals; they should not appear on the Financial Proposals to be submitted.}

Financial Proposal Standard Forms shall be used for the preparation of the Financial Proposal according to the instructions provided in Section 2.

FIN-1 Financial Proposal Submission Form

FIN-2 Summary of Costs

FIN-3 Breakdown of Remuneration, including Appendix A “Financial Negotiations - Breakdown of Remuneration Rates” in the case of QBS method

FIN-4 Reimbursable expenses

**Form FIN-1**

**Financial Proposal Submission Form**

{Location, Date}

To: [Name and address of Client]

Dear Sirs:

We, the undersigned, offer to provide the consulting services for [Insert title of assignment] in accordance with your Request for Proposal dated [Insert Date] and our Technical Proposal.

Our attached Financial Proposal is for the amount of {Indicate the corresponding to the amount(s) currency(ies)}{Insert amount(s) in words and figures}, *[Insert “including” or “excluding”] of all indirect local taxes in accordance with Clause 25.1 in the Data Sheet.* The estimated amount of local indirect taxes is {Insert currency} {Insert amount in words and figures} which shall be confirmed or adjusted, if needed, during negotiations. {Please note that all amounts shall be the same as in Form FIN-2}.

Our Financial Proposal shall be binding upon us subject to the modifications resulting from Contract negotiations, up to expiration of the validity period of the Proposal, i.e. before the date indicated in Clause 12.1 of the Data Sheet.

Commissions and gratuities paid or to be paid by us to an agent or any third party relating to preparation or submission of this Proposal and Contract execution, paid if we are awarded the Contract, are listed below:

Name and Address Amount and Purpose of Commission

of Agents Currency or Gratuity

{If no payments are made or promised, add the following statement: “No commissions or gratuities have been or are to be paid by us to agents or any third partyrelating to this Proposal and Contract execution.”}

We understand you are not bound to accept any Proposal you receive.

We remain,

Yours sincerely,

Authorized Signature {In full and initials}:

Name and Title of Signatory:

In the capacity of:

Address:

E-mail: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

{For a joint venture, either all members shall sign or only the lead member/consultant, in which case the power of attorney to sign on behalf of all members shall be attached}

**Form FIN-2Summary of Costs**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | **Cost** | | | |
| {Consultant must state the proposed Costs in accordance with Clause **16.4 of the Data Sheet**; delete columns which are not used} | | | |
| {*Insert Foreign Currency # 1*} | {*Insert Foreign Currency # 2, if used*} | {*Insert Foreign Currency # 3,if used*} | {*Insert*  *Local Currency, if used and/or required (16.4 Data Sheet*} |
| **Cost of the Financial Proposal** |  |  |  |  |
| Including: |  |  |  |  |
| (1) **Remuneration** |  |  |  |  |
| (2)**Reimbursables** |  |  |  |  |
| **Total Cost of the Financial Proposal:**  {Should match the amount in Form FIN-1} |  |  |  |  |
| **Indirect Local Tax Estimates – to be discussed and finalized at the negotiations if the Contract is awarded** | | | | |
| 1. {insert type of tax. e.g., VAT or sales tax} |  |  |  |  |
| 1. {e.g., income tax on non-resident experts} |  |  |  |  |
| 1. {insert type of tax} |  |  |  |  |
| Total Estimate for Indirect Local Tax: |  |  |  |  |

**Footnote: Payments will be made in the currency(ies) expressed above (Reference to ITC 16.4).**Form FIN-3 Breakdown of Remuneration

When used for Lump-Sum contract assignment, information to be provided in this Form shall only be used to demonstrate the basis for the calculation of the Contract’s ceiling amount;to calculate applicable taxes at contract negotiations; and, if needed, to establish payments to the Consultant for possible additional services requested by the Client. This Form shall not be used as a basis for payments under Lump-Sum contracts

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **A. Remuneration** | | | | | | | | |
| **No.** | **Name** | **Position (as in TECH-6)** | **Person-month Remuneration Rate** | **Time Input in Person/Month**  (from TECH-6) | {*Currency # 1- as in FIN-2*} | {*Currency # 2- as in FIN-2}* | *{Currency# 3- as in FIN-2*} | {*Local Currency- as in FIN-2}* |
|  | **Key Experts** |  |  |  |  |  |  |  |
| K-1 |  |  | [*Home*] |  |  |  |  |  |
|  | [*Field*] |  |  |  |  |  |
| K-2 |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  | **Non-Key Experts** |  |  |  |  |  |  |  |
| N-1 |  |  | [*Home*] |  |  |  |  |  |
| N-2 | [*Field*] |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  | Total Costs |  |  |  |  |

Appendix A.Financial Negotiations - Breakdown of Remuneration Rates

1. **Review of Remuneration Rates**
   1. The remuneration rates are made up of salary or a base fee, social costs, overheads, profit, and any premium or allowance that may be paid for assignments away from headquarters or a home office. An attached Sample Form can be used to provide a breakdown of rates.
   2. If the RFP requests submission of a technical proposal only, the Sample Form is used by the selected Consultant to prepare for the negotiations of the Contract. If the RFP requests submission of the financial proposal, the Sample Form shall be completed and attached to the Financial Form-3. Agreed (at the negotiations) breakdown sheets shall form part of the negotiated Contract and included in its Appendix D or C.
   3. At the negotiations the firm shall be prepared to disclose its audited financial statements for the last three years, to substantiate its rates, and accept that its proposed rates and other financial matters are subject to scrutiny. The Client is charged with the custody of government funds and is expected to exercise prudence in the expenditure of these funds.
   4. Rate details are discussed below:
2. Salary is the gross regular cash salary or fee paid to the individual in the firm’s home office. It shall not contain any premium for work away from headquarters or bonus (except where these are included by law or government regulations).
3. Bonusesare normally paid out of profits. To avoid double counting, any bonuses shall not normally be included in the “Salary” and should be shown separately. Where the Consultant’s accounting system is such that the percentages of social costs and overheads are based on total revenue, including bonuses, those percentages shall be adjusted downward accordingly. Where national policy requires that 13 months’ pay be given for 12 months’ work, the profit element need not be adjusted downward. Any discussions on bonuses shall be supported by audited documentation, which shall be treated as confidential.
4. Social Charges are the costs of non-monetary benefits and may include, inter alia, social security (including pension, medical, and life insurance costs) and the cost of a paid sick and/or annual leave. In this regard, a paid leave during public holidays or an annual leave taken during an assignment if no Expert’s replacement has been provided is not considered social charges.
5. Cost of Leave. The principles of calculating the cost of total days leave per annum as a percentage of basic salary is normally calculated as follows:

Leave cost as percentage of salary = 

Where w = weekends, ph = public holidays, v = vacation, and s = sick leave.

Please note that leave can be considered as a social cost only if the Client is not charged for the leave taken.

1. Overheadsare the Consultant’s business costs that are not directly related to the execution of the assignment and shall not be reimbursed as separate items under the Contract. Typical items are home office costs (non-billable time, time of senior Consultant’s staff monitoring the project, rent of headquarters’ office, support staff, research, staff training, marketing, etc.), the cost of Consultant’s personnel not currently employed on revenue-earning projects, taxes on business activities, and business promotion costs. During negotiations, audited financial statements, certified as correct by an independent auditor and supporting the last three years’ overheads, shall be available for discussion, together with detailed lists of items making up the overheads and the percentage by which each relates to basic salary. The Client does not accept an add-on margin for social charges, overhead expenses, etc. for Experts who are not permanent employees of the Consultant. In such case, the Consultant shall be entitled only to administrative costs and a fee on the monthly payments charged for sub-contracted Experts.
2. Profitis normally based on the sum of the Salary, Social costs, and Overheads. If any bonuses paid on a regular basis are listed, a corresponding reduction shall be made in the profit amount. Profit shall not be allowed on travel or any other reimbursable expenses.
3. Away from Home Office Allowance or Premium or Subsistence Allowances.Some Consultants pay allowances to Experts working away from headquarters or outside of the home office. Such allowances are calculated as a percentage of salary (or a fee) and shall not draw overheads or profit. Sometimes, by law, such allowances may draw social costs. In this case, the amount of this social cost shall still be shown under social costs, with the net allowance shown separately.

UNDP standard rates for the particular country may be used as reference to determine subsistence allowances.

**Sample Form**

Consultant: Country:

Assignment: Date:

**Consultant’s Representations Regarding Costs and Charges**

We hereby confirm that:

(a) the basic fees indicated in the attached table are taken from the firm’s payroll records and reflect the current rates of the Experts listed which have not been raised other than within the normal annual pay increase policy as applied to all the Consultant’s Experts;

(b) attached are true copies of the latest pay slips of the Experts listed;

(c) the away- from-home office allowances indicated below are those that the Consultant has agreed to pay for this assignment to the Experts listed;

(d) the factors listed in the attached table for social charges and overhead are based on the firm’s average cost experiences for the latest three years as represented by the firm’s financial statements; and

(e) said factors for overhead and social charges do not include any bonuses or other means of profit-sharing.

[Name of Consultant]

Signature of Authorized Representative Date

Name:

Title:

**Consultant’s Representations Regarding Costs and Charges**

**(Model Form I)**

(Expressed in {insert name of currency\*})

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Personnel | | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| Name | Position | Basic Remuneration Rate per Working Month/Day/Year | Social Charges1 | Overhead1 | Subtotal | Profit2 | Away from Home Office Allowance | Proposed Fixed Rate per Working Month/Day/Hour | Proposed Fixed Rate per Working Month/Day/Hour1 |
| Home Office | |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
| Client’s Country | |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |

{\* If more than one currency is used, use additional table(s), one for each currency}

1. Expressed as percentage of 1

2. Expressed as percentage of 4

**Form FIN-4 Breakdown of Reimbursable Expenses**

When used for Lump-Sum contract assignment, information to be provided in this Form shall only be used to demonstrate the basis for calculation of the Contract ceiling amount, to calculate applicable taxes at contract negotiations and, if needed, to establish payments to the Consultant for possible additional services requested by the Client. This form shall not be used as a basis for payments under Lump-Sum contracts

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **B. Reimbursable Expenses** | | | | | | | | |
| **N°** | **Type of Reimbursable Expenses** | **Unit** | **Unit Cost** | **Quantity** | {Currency # 1- as in FIN-2} | {Currency # 2- as in FIN-2} | {Currency# 3- as in FIN-2} | {Local Currency- as in FIN-2} |
|  | {e.g., Per diem allowances\*\*} | {Day} |  |  |  |  |  |  |
|  | {e.g., International flights} | {Ticket} |  |  |  |  |  |  |
|  | {e.g., In/out airport transportation} | {Trip} |  |  |  |  |  |  |
|  | {e.g., Communication costs between Insert place and Insert place} |  |  |  |  |  |  |  |
|  | { e.g., reproduction of reports} |  |  |  |  |  |  |  |
|  | {e.g., Office rent} |  |  |  |  |  |  |  |
|  | .................................... |  |  |  |  |  |  |  |
|  | {Training of the Client’s personnel – if required in TOR} |  |  |  |  |  |  |  |
| Total Costs | | | | |  |  |  |  |

Legend*:*

“Per diem allowance” is paid for each night the expert is required by the Contract to be away from his/her usual place of residence. Client can set up a ceiling.

# Section 5. Eligible Countries

**In reference to ITC6.3.2,** for the information of shortlisted Consultants, at the present time firms, goods and services from the following countries are excluded from this selection:

Under the ITC 6.3.2 (a): None

Under the ITC 6.3.2 (b): None

# Section 6. Bank Policy – Corrupt and Fraudulent Practices

(this Section 6 shall not be modified)

**Guidelines for Selection and Employment of Consultants under IBRD Loans and IDA Credits &Grants by World Bank Borrowers, dated January 2011:**

“**Fraud and Corruption**

1.23 It is the Bank’s policy to require that Borrowers (including beneficiaries of Bank loans), consultants, and their agents (whether declared or not), sub-contractors, sub-consultants, service providers, or suppliers, and any personnel thereof, observe the highest standard of ethics during the selection and execution of Bank-financed contracts [footnote: In this context, any action taken by a consultant or any of its personnel, or its agents, or its sub-consultants, sub-contractors, services providers, suppliers, and/or their employees, to influence the selection process or contract execution for undue advantage is improper.]. In pursuance of this policy, the Bank:

(a) defines, for the purposes of this provision, the terms set forth below as follows:

1. “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party[[2]](#footnote-2);
2. “fraudulent practice” is any act or omission, including misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial or other benefit or to avoid an obligation[[3]](#footnote-3);
3. “collusive practices” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party[[4]](#footnote-4);
4. “coercive practices” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party[[5]](#footnote-5);
5. “obstructive practice” is

(aa) deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive, or collusive practice; and/or threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or

(bb) acts intended to materially impede the exercise of the Bank’s inspection and audit rights;

(b) will reject a proposal for award if it determines that the consultant recommended for award or any of its personnel, or its agents, or its sub-consultants, sub-contractors, services providers, suppliers, and/or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;

(c) will declare mis procurement and cancel the portion of the Loan allocated to a contract if it determines at any time that representatives of the Borrower or of a recipient of any part of the proceeds of the Loan were engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the selection process or the implementation of the contract in question, without the Borrower having taken timely and appropriate action satisfactory to the Bank to address such practices when they occur, including by failing to inform the Bank in a timely manner they knew of the practices;

(d) will sanction a firm or an individual at any time, in accordance with prevailing Bank’s sanctions procedures[[6]](#footnote-6), including by publicly declaring such firm or an ineligible, either indefinitely or for a stated period of time: (i) to be awarded a Bank-financed contract, and (ii) to be a nominated[[7]](#footnote-7) sub-consultant, supplier, or service provider of an otherwise eligible firm being awarded a Bank-financed contract.

# Section 7. Terms of Reference

**Terms of Reference for**

**Development of a‘Advanced Draft’ BenefitSharing Plan for the Emission Reductions Program in 13 districts of Nepal's Terai Arc Landscape**

# Background

Nepal is one of the REDD+ (Reducing Emission from Deforestation and Forest Degradation plus Role of Conservation, Sustainable Management of Forests and Carbon Stocks Enhancement) countries operating under the World Bank's Forest Carbon Partnership Facility (FCPF) for its REDD+ Readiness. Nepal's Emission Reduction Program Document (ERPD) has been endorsed by the Carbon Fund. Earlier in 2014, Carbon Fund Participants competitively selected Nepal's ER-PIN and authorized the World Bank to support the development of a full ERPD. The Bank and the Government of Nepal (GoN) signed a Letter of Intent (LOI) in June 2015 formalizing the Bank’s supporting role and indicating a national volume of emission reductions the Carbon Fund intends to pay for upon verification of results.

Nepal has participated in REDD+ readiness since 2008. The REDD Implementation Centre under the Ministry of Forests and Environment coordinates Nepal's REDD+ under the REDD Working Group in collaboration with a number of REDD+ actors and stakeholders including government agencies, civil societies, indigenous peoples, local communities and development partners. Besides other agencies, the World Bank, through FCPF, is supporting the GoN in its REDD+ readiness and associated activities. Under the Readiness Fund of FCPF, a grant of $3.6 million was signed with the GoN in 2011 to help the country get ready for REDD+ through technical studies, policy formulation, consultations and capacity building activities. The REDD+ Readiness Grant ended in August 2015. An additional grant agreement was signed between the World Bank and the GoN in early 2017 for US$ 5.2 million, which is allowing the Governmentto undertake a number of additional readiness preparation activities including preparation of a Benefit Sharing Plan.

Nepal’s ERPD for the Terai Arc Landscape was accepted into Carbon Fund Portfolio during the Carbon Fund meeting held from June 20 to 22, 2018 in Paris, France. The approved ERPD has proposed seven major interventions including sustainable management of community-based forests in the 13 Terai districts.

The main objectives of the ER program in the TALare 1) to address key drivers and expanding sustainable management of forests, 2) to ensure fair and equitable benefit sharing of carbon and non-carbon benefits and 3) to increase livelihood opportunities for poor and forest-dependent communities. In its first 10 years,the ER Program aims to reduce emissions by 34.2MtCO2e, and these benefits are expected to increase over time given the long-term nature of the planned interventions.

Criterion 30 of FCPF Methodological Framework requires that the Benefit Sharing Plan will elaborate on the benefit-sharing arrangements for the monetary and non-monetary benefits, building on the description in the ER Program Document, and taking into account the importance of managing expectations among potential Beneficiaries. Criterion from 30 to 33 of the Methodological Framework discuss about benefit-sharing plan, while Criterion 34 and 35 discuss on non-carbon benefits. In line with these Criteria, Chapter 15 of Nepal's ERPD describes 'benefit sharing arrangements', under which major potential beneficiaries have been identified, while at the same time, it provides basic guidance for monetary and non-monetary benefits of emission reduction program. Chapter 16 describes non-carbon benefits of the program. The “Note on Benefit Sharing for Emission Reductions Programs under the Forest Carbon Partnership Facility and Bio Carbon Fund Initiative for Sustainable Forest Landscapes”, 2019 version requires that at least an advanced draft Benefit Sharing Plan must be made publicly available in English prior to ERPA signature and disclosed in a form, manner, and language understandable to the affected stakeholders for the ER Program.

Nepal intends to enter into ERPA within 2019 and therefore it needs at least an advanced draft Benefit Sharing Plan publicly available in both English and Nepali language. Therefore, the major aim of this assignment is to prepare an advanced draft Benefit Sharing Plan in both English and Nepali language.

# Objectives

The overall objective of this assignment is to prepare an advanced draft Benefit Sharing Plan for the ER Program of Nepal's Terai Arc Landscape. Specific objectives include:

* To identify different options for sharing monetary and non-monetary carbon benefits among stakeholders and assess the advantages and disadvantages of these options to the Program, including the costs involved;
* To develop an advanced draft Benefit Sharing Plan both in English and Nepali based on the best option selected by the stakeholders, building on the benefit sharing arrangements articulated in the ERPD;
* To customize a grievance redress mechanism (GRM) built on best practices and the national GRM report; and

# Scope of Work

The consulting firm will undertake the following tasks:

1. Define the percentage of revenue to be shared among different rights holders and stakeholders in each beneficiary group (government at each level; local communities; forest users; IPs, women, Dalits, Madhesi and other marginalized groups) and related civil societies existing in the ER Program area. The question to be answered to address this include:
2. What kind of criteria should be used for defining the percentage share that goes to each eligible stakeholder group?
3. What is the administrative and MRV cost of ER payment required for ensuring ERs to be generated based on the available experience globally and which entity/-ies will administer the ER payment? What linkage does this cost have with the percentage share that goes to this entity?
4. How to ensure that the operational costs are covered prior to “sharing” the revenues?
5. How much of the revenue has to be transferred to community primarily contributing to ER and why and how much of it (if any) should go to government and other stakeholders?
6. What kind of potential economically viable activities are there in which communities could invest their ER payments?
7. What type of benefits can be generated by leveraging the ER payment to implement activities contributing to economic development of the rural community, improved NRM and overall environmental sustainability?
8. What types of potential activities for investment of ER payment are most likely to sustain and improve the ecosystem services?
9. Define the criteria for distributing the ER payment (benefit) to different communities within the region once the share to communities from the program is defined. The questions to be answered include:
10. How should performance of different communities/interest groups at local level be measured?
11. Who should prioritize the investments, given that funds are unlikely to cover the needs of all those communities within the ER Program area at once?
12. Who will bear the risk if one community group or actor does not deliver the result?
13. Who represents rights holders and stakeholders groups? What is the minimum requirement for them to be eligible for claiming benefits?
14. Identify and assess options to channel results-based payment funds to local communities and develop an advanced draft Benefit Sharing Plan for the option agreed upon by the main stakeholders (federal govt, state govt, local govt and diverse local rights-holders including forest communities, IPs, Women, Dalit, Madhesi and other marginalized). The questions to be addressed in this assessment include:
15. What financial structure/mechanisms should be set up for the management and disbursement of funds and how should this be managed? For example, could management be done by a Government Program Management Unit, or creation of a trust fund, etc.? How can funds be managed prior to the operationalization of the proposed structure / mechanism?
16. What is the best mechanism to ensure that funds reach communities in a cost-efficient way? Particular attention should be paid to how the funds would create incentives to local communities for the adoption of land use practices conducive to REDD+? In order to answer this question, the consultant is required to assess funds disbursement options related to rural development and biodiversity conservation in the ER program area.
17. Define the roles and responsibilities of each beneficiary group with regard to meeting the requirements of the ERPA. The questions to be answered include:
18. What are the roles and responsibilities of each beneficiary group? How will these roles and responsibilities be linked to the provisions of the Benefit Sharing Plan?
19. How can compliance with agreed roles and responsibilities be monitored? How can the monitoring system currently under preparation be used in guiding benefit sharing across beneficiaries? What role could participatory monitoring have in informing the benefit sharing mechanism? To respond to this question, the consultants are expected to refer to the Monitoring Framework for the program.
20. How can grievances from program participants be treated? The consultant is expected to customize the grievance redress mechanism proposed in the ERPD so that it can handle benefit sharing-related grievances, building on best practices and the national GRM report.
21. How and when should the Benefit Sharing Plan be updated?

The identified options should be assessed against a transparent list of criteria, including but not limited to: i) effectiveness (to what extent does the mechanism proposed address the drivers of deforestation and forest degradation); ii) efficiency (what are the costs associated with running the mechanism; and iii) equity in ensuring all relevant stakeholders are duly benefited (to what extent the proposed mechanism promote fairness).

# Approach

## Process

The assignment will include a thorough review of available literature and comprehensive, structured consultations with all major stakeholders at the national, provincial, and especially the local/district levels. The following activities are envisaged:

1. Revisit and review the monetary, non-monetary and non-carbon benefits identified in the ERPD and identify the additional benefits (if any) from the consultation process;
2. In-depth review of the relevant policy documents (ERPD, ESMF, REDD+ strategy, GRM report, MRV report, and other relevant readiness reports, etc.), other related documents;
3. Conduct six multi-stakeholder consultations covering 13 TAL districts and one national level consultation;
4. Propose a comprehensive mechanism for sharing benefits arising from the ER program intervention (carbon money). The assignment should identify main risks and provide concrete suggestions on how the government can move forward in establishing a national framework for sharing benefits from REDD+ programs;
5. Share the draft mechanism with key experts, policy makers and representatives of related rights holders before finalizing the advanced draft Benefit Sharing Plan; and
6. Multi-stakeholder consultations and preparation of advanced draft 0Benefit Sharing Plan, including a proposal for a benefit sharing architecture for the 13TAL districts but with potential for future adoption at the national level. The proposal should not require a substantial shift in current land and forest policies to be viable. The assignment should identify main risks and provide concrete suggestions on how the government can move forward in establishing a national framework for sharing benefits from REDD+ programs.

## Team

The team for this assignmentwill consist of the following members:

1. **Team Leader**

**Roles and Responsibilities:**The team Leader, in close coordination with and under the guidance of the technical committee formed to oversee this assignment at the REDD IC, will lead the team for this assignment. Specific roles and responsibilities of the team leader include:

* Review and analyze the guiding documents for benefit sharing plans of relevant cases in national and international arena;
* Review and analyze National Forest Policy, 2019, Forestry Sector Strategy (2015-25), Nepal National REDD+ Strategy (2018), Nepal’s Emission Reduction Program Document, 2018 and associated safeguards related documents;
* Review benefit-sharing plans of REDD+ in other countries;
* Review documents related to Forest Carbon Partnership Facility, including, but are not limited to, FCPF Methodological Framework, 2013, Note on Benefit Sharing for Emission Reductions Programs Under the Forest Carbon Partnership Facility and Bio Carbon Fund Initiative for Sustainable Forest Landscapes, 2019, Note on the Ability of Program Entity to Transfer Title to Emission Reductions (ERs), 2018, World Bank Safeguard Policies and the UNFCCC REDD+ Safeguards, 2013 and ISFL ER Program Requirements;
* Review and analyze issues related to forestland tenure, fair and equitable benefit sharing, climate justice, results-based payments;
* Coordinate consultation meetings with the technical committee and other senior officials from the Ministry, REDD IC and other stakeholders; and
* Coordinate within the team to prepare documents including inception report and advanced draft Benefit Sharing Plan.

**Required qualification:** The team leader must have the following qualification and experience:

* Hold a PhD degree in forest economics, forestry, natural resources, environmental management or REDD+ with a minimum 10 and preferably 15 years of relevant experiences preferably in different countries;
* Good understanding of the benefit-sharing issues related to community-based forestry, climate change and REDD+;
* In-depth knowledge and understanding of issues pertaining to natural resources including land and forest tenure, fair and equitable benefit sharing, climate justice, result-based payment and payment for ecosystem services;
* In-depth research-based knowledge, expertise and experiences in forest governance, community-based forestry, sustainable forest management including forest certification, and benefit-cost analysis;
* Proven ability to work in an interdisciplinary manner, both independently and in a team;
* Excellent interpersonal and networking skills, especially in multi-stakeholder contexts; and
* Experience and exposure on REDD+ issues in national and international arena.
* Scientific publication in forestry, governance, climate change, REDD+ and related areas will be an added advantage

1. **REDD+ Expert:**

**Roles and responsibilities:** The REDD+ expert will report to the team leader. She/he will work under the guidance of the team leader in close collaboration and consultation with the focal point for the assignment at the REDD IC. She/he will specifically be responsible to:

* Access, review and analyze international and national climate change policies and measures including national REDD+ strategy, ER-PD and Forest Investment Plan of Nepal;
* Present current status of REDD+ process in Nepal, opportunities and challenges for implementation of the ER programs;
* Review and analyze the guiding documents for benefit sharing plans of relevant cases in national and international arena and facilitate the local communities in understanding these issues;
* Review and analyze Forest Policy, Forestry Sector Strategy, REDD+ Strategy, ER-PD, FIP as well as other forestry, environment and climate change related policies, strategies and documents;
* Identify and engage relevant REDD+ Stakeholders as well as application of principles that are key to REDD+ Implementation such as FPIC; and
* Contribute to developing advanced draft Benefit Sharing Plan with other team members.

**Required qualification and experience:** The REDD+ Expert should possess the following qualification and experiences:

* Hold at least a Masters degree in forestry, REDD+, Climate Change, Environmental Science;
* Have at least 10 years of working experience on climate change, REDD+ and other relevant projects in Nepal and/or developing countries;
* Demonstrate technical capacity, including analytical skills, and proven track record in delivering multi-sectoral, complex programs;
* Good understanding of climate change policy, REDD+, forestry programs and plans in Nepal and at global scale;
* Sound knowledge on forestry sector institutions, current program implementation arrangements and process in Nepal; and
* Effective communication skills.
* **Publication and experience on REDD+ will be added as an advantage.**

1. **Gender Expert:**

**Roles and responsibilities:** The Gender Expert will report to the team leader. She/he will work under the guidance of the team leader in close collaboration and consultation with REDD IC focal point for the assignment. She/he will specifically be responsible to:

* Identify, plan and conduct analytical work that assesses ER program benefits to local communities, considering gender and poverty-sensitive aspects of the program;
* Access, review and analyze gender related policies, programs, activities and other published/unpublished documents unfolding international and national level;
* Estimate tentative costs and benefit for gender related activities in implementation of the Benefit Sharing Program;
* Prepare a report detailing potential project activities, sites, targeted groups, stakeholders and their roles and responsibilities, estimated costs, expected outcomes of the proposed project activities;
* Conduct gender focused group discussions and include the outcomes of the discussion in the plan;
* Ensure women from each target group---government officials, community groups, private sector, indigenous peoples, Dalits, Madhesis and other marginalized communities participate in all consultations, preferably 50 per cent as far as possible
* Participate in consultation meetings as required; and
* Contribute to developing advanced draft Benefit Sharing Plan with other team members

**Required qualification and experience:** The consultant should possess the following qualification and experiences**:**

* Hold at least a Master's degree in social development, gender, women studies, development studies, social forestry, conflict management, or related disciplines;
* Demonstrated skills and experiences in dealing with gender related issues particularly in the forestry sector;
* Should have at least five years of experience in community development or rural development, with familiarity of issues on gender, social, cultural and local reality;
* Possess strong knowledge of land tenure, access to and ownership and access/user rights, to include understanding of customary land rights;
* Be familiar with participatory rural appraisal and social issues associated with NRM in Nepal and the REDD+ safeguard policies; and
* Strong skills in facilitating the multi stakeholder workshops and consultation.
* Experiences in gender related works particularly in REDD+ and other forestry related programs and projects
* **Women candidate is strongly desirable for this position.**

1. **Social Inclusion expert:**

**Roles and responsibilities:** The Social Inclusion Expert will report to the team leader. She/he will work under the guidance of the team leader in close collaboration and consultation with REDD IC focal point for the assignment. She/he will specifically be responsible to:

* Identify, plan and conduct analytical work that assesses ER program benefits to local communities, considering Social Inclusion and poverty-sensitive aspects of the program;
* Access, review and analyze social inclusion related policies, programs, activities and other published/unpublished documents unfolding international and national level;
* Estimate tentative costs and benefit for social inclusion related activities in implementation of the Benefit Sharing Program;
* Prepare a report detailing potential project activities, sites, targeted groups, stakeholders and their roles and responsibilities, estimated costs, expected outcomes of the proposed project activities;
* Conduct focus group discussions and include the outcomes of the discussion in the plan;
* Ensure Indigenous Peoples and Local Communities including women, indigenous peoples, Dalits, Madhesis, community-based forestry groups and other marginalized communities participate in consultations
* Participate in consultation meetings as required; and
* Contribute to developing the benefit sharing plan with other team members.

**Required qualification and experience:** The consultant should possess the following qualification and experiences**:**

* Hold at least a Master's degree in social development, development studies, diversity management, social forestry, conflict management, or related disciplines;
* Demonstrated skills and experiences in dealing with Social Inclusion related issues particularly in the forestry sector;
* Should have at least five years of experience in community development or rural development, with familiarity of issues on social dynamics, inclusion and diversity management, cultural and local reality;
* Possess strong knowledge of land tenure, access to land ownership and access/user rights, to include understanding of customary land rights;
* Be familiar with issues related to Indigenous Peoples and Local Communities in common pool resources, biodiversity, REDD+ and climate change.
* Be familiar with participatory rural appraisal and social issues associated with NRM in Nepal and the REDD+ safeguard policies; and
* Strong skills in facilitating the multi stakeholder workshops and consultation.

1. **Legal expert:**

**Roles and responsibilities:** The Legal Expert will report to the team leader. She/he will work under the guidance of the team leader in close collaboration and consultation with REDD IC focal point for the assignment. She/he will specifically be responsible to:

* Identify the legal, policy and institutional issues related to benefit sharing of common pool resources, such as community-based forests, natural resources, ecosystem services including emission reduction;
* Contribute to the development of the BSM for the ER Program, to make sure that it complies with existing related national and international policies and measures (Nepali laws, regulations, guidelines etc) including FCPF Methodological Framework and Note on Benefit Sharing for Emission Reductions Programs Under the Forest Carbon Partnership Facility and Bio Carbon Fund Initiative for Sustainable Forest Landscapes, 2019
* Consult legal experts and government offices, such as the Ministry of Law, Justice and Parliamentary Affairs, Ministry of Finance, Natural Resources and Fiscal Commission and National Planning Commission that are directly related to Benefit Sharing Plan.
* Participate in consultation meetings as required; and
* Contribute to developing advanced draft Benefit Sharing Plan with other team members.

**Required qualification and experience:** The consultant should possess the following qualification and experiences**:**

* Hold at least a Master's degree in Law and expertise in natural resources governance;
* Should have minimum of 5 and preferably 7 years of experience in legal issues related to natural resources and forestry;
* Be familiar with political, administrative, legal, social, economic and cultural issues associated with common pool resources including REDD+
* Should have a good understanding of Nepal’s administrative and forest governance structures, land and forest resource tenure issues, title to emission reductions; and
* Should have knowledge of international environmental agreements, Nepal’s REDD+ readiness process, relevant laws and policies.

**In addition, the firm can hire local facilitators as part of the necessary arrangements for stakeholder consultations.**

## Work Plan

The team is required to prepare and submit an inception report with a detailed work plan before the assignment officially commences. The work plan should describe how the required work will be carried out; it should include a schedule, methodology for each activity as well as type and nature of information to be collected and analyzed. The work plan will be reviewed by the REDD IC and later finalized jointly by the team and the REDD IC.

# Qualifications/Experience of the Consulting Firm/ Consortium

This opportunity is open to relevant service providing firms. The firms must be duly registered in Nepal and be able to produce up-to-date tax clearance certificates.

The consulting firm/consortium for this assignment should have a demonstrated ability and relevant experience in (i) leading multi-disciplinary teams, (ii) successfully completing assignments in REDD+, forestry, environment management or climate change, and (iii) producing comprehensive and quality documents and reports.

The followings are criteria for potential firms/consortium.

The firm/consortiumfor this assignmentshould provide evidences of the following:

* Number of experts in the relevant field including REDD+, forestry, climate change, environmental management, Nepalese law, gender and social inclusion, economic analysis
* Experiences of the firm/consortium in donor-funded programs
* Experiences of the firm/consortium in REDD+ and/or forestry and/or climate change and/or environmental management and/or clean development mechanism
* International experiences (at least the team leader);

# Duration of Work

This assignment should be completed by July 5, 2019.

**6.1 Deliverables**

**The following deliverables are mandatory. The delivery time of these documents should be clearly specified in the full proposal.**

1. Inception report in English (1 week after signing the contract)
2. A mid-term report in English after the field consultations
3. Advanced Draft Benefit Sharing Plan in English
4. Advanced Draft Benefit Sharing Plan in Nepali
5. Minutes of consultations with stakeholders in Nepali

All deliverables should be submitted to REDD Implementation Centre.

# Selection Process and Criteria

Selection process of the qualified firm/consultant/organization will start from advertising for “Expression of Interest (EoI)”. The shortlisted firms/consultant/organization based on EoIs submitted will be requested to submit the full proposal following The World Bank Procurement Regulations for IPF Borrowers, July 2016 Revised November 2017 and August 2018.

**8. Application Procedure**

Eligible firm/consultant/organization of the firms should submit “Expression of Interest (EoI)” with the following documents:

* Letter of EoI
* Profile of the firm
* Copy of registration and renewal certificates
* Roster of experts
* Copy of annual audit report for last three years and tax clearance certificate
* Letter from partnering firm/institution if joint venture is proposed.

Only shortlisted firms/consortiums will be requested to submit the full proposal

**9. ContactPerson**

Shankar Adhikari

REDD Implementation Centre

Babarmahal, Kathmandu, Nepal

Tel: 977-1-4239126

Fax: 977-1-4215261

E-mail: [info@redd.gov.np](mailto:info@mofsc-redd.gov.np)

# PART II

# Section 8. Conditions of Contract and Contract Forms

**Foreword**

1. Part II includes two types of standard Contract forms for Consulting Services (a Time-Based Contract and a Lump-Sum Contract) that are based on the contract forms included in the harmonized Standard Request for Proposals (Master Document for Selection of Consultants prepared by participating Multilateral Development Banks (MDBs).
2. **Time-Based Contract**. This type of contract is appropriate when it is difficult to define or fix the scope and the duration of the services, either because they are related to activities carried out by others for which the completion period may vary, or because the input of the consultants required for attaining the objectives of the assignment is difficult to assess. In time-based contracts the Consultant provides services on a timed basis according to quality specifications, and Consultant’s remuneration is determined on the basis of the time actually spent by the Consultant in carrying out the Services and is based on (i) agreed upon unit rates for the Consultant’s experts multiplied by the actual time spent by the experts in executing the assignment, and (ii) reimbursable expenses using actual expenses and/or agreed unit prices. This type of contract requires the Client to closely supervise the Consultant and to be involved in the daily execution of the assignment.
3. **Lump-Sum Contract.** This type of contract is used mainly for assignments in which the scope and the duration of the Services and the required output of the Consultant are clearly defined. Payments are linked to outputs (deliverables) such as reports, drawings, bill of quantities, bidding documents, or software programs. Lump-sum contracts are easier to administer because they operate on the principle of a fixed price for a fixed scope, and payments are due on clearly specified outputs and milestones. Nevertheless, quality control of the Consultant’s outputs by the Client is paramount.
4. The templates are designed for use in assignments with consulting firms and shall not be used for contracting of individual experts. These standard Contract forms are to be used for complex and/or large value assignments, and/or for contracts above US$300,000 equivalent or more unless otherwise approved by the Bank.

**STANDARD FORM OF CONTRACT**

**Consultant’s Services**

Lump-Sum

**Contents**

[**Preface** 67](#_Toc300749250)

[**I.Form of Contract** 69](#_Toc300749251)

[**II.General Conditions of Contract** 73](#_Toc300749252)

[**A. General Provisions** 73](#_Toc300749253)

[1.Definitions 73](#_Toc300749254)

[2.Relationship Between the Parties 74](#_Toc300749255)

[3.Law Governing Contract 75](#_Toc300749256)

[4.Language 75](#_Toc300749257)

[5.Headings 75](#_Toc300749258)

[6.Communications 75](#_Toc300749259)

[7.Location 75](#_Toc300749260)

[8.Authority of Member in Charge 75](#_Toc300749261)

[9.Authorized Representatives 75](#_Toc300749262)

[10.Corrupt and Fraudulent Practices 75](#_Toc300749263)

[**B. Commencement, Completion, Modification and Termination of Contract** 76](#_Toc300749264)

[11.Effectiveness of Contract 76](#_Toc300749265)

[12.Termination of Contract for Failure to Become Effective 76](#_Toc300749266)

[13.Commencement of Services 76](#_Toc300749267)

[14.Expiration of Contract 76](#_Toc300749268)

[15.Entire Agreement 76](#_Toc300749269)

[16.Modifications or Variations 76](#_Toc300749270)

[17.Force Majeure 76](#_Toc300749271)

[18.Suspension 78](#_Toc300749272)

[19.Termination 78](#_Toc300749273)

[**C. Obligations of the Consultant** 80](#_Toc300749274)

[20.General 80](#_Toc300749275)

[21.Conflict of Interests 81](#_Toc300749276)

[22.Confidentiality 82](#_Toc300749277)

[23.Liability of the Consultant 82](#_Toc300749278)

[24.Insurance to be Taken out by the Consultant 82](#_Toc300749279)

[25.Accounting, Inspection and Auditing 83](#_Toc300749280)

[26.Reporting Obligations 83](#_Toc300749281)

[27.Proprietary Rights of the Client in Reports and Records 83](#_Toc300749282)

[28.Equipment, Vehicles and Materials 83](#_Toc300749283)

[**D. Consultant’s Experts and Sub-Consultants** 84](#_Toc300749284)

[29.Description of Key Experts 84](#_Toc300749285)

[30.Replacement of Key Experts 84](#_Toc300749286)

[31.Removal of Experts or Sub-consultants 84](#_Toc300749287)

[**E. Obligations of the Client** 85](#_Toc300749288)

[32.Assistance and Exemptions 85](#_Toc300749289)

[33.Access to Project Site 85](#_Toc300749290)

[34.Change in the Applicable Law Related to Taxes and Duties 86](#_Toc300749291)

[35.Services, Facilities and Property of the Client 86](#_Toc300749292)

[36.Counterpart Personnel 86](#_Toc300749293)

[37.Payment Obligation 86](#_Toc300749294)

[**F. Payments to the Consultant** 86](#_Toc300749295)

[38.Contract Price 86](#_Toc300749296)

[39.Taxes and Duties 87](#_Toc300749297)

[40.Currency of Payment 87](#_Toc300749298)

[41.Mode of Billing and Payment 87](#_Toc300749299)

[42.Interest on Delayed Payments 88](#_Toc300749300)

[**G. Fairness and Good Faith** 88](#_Toc300749301)

[43.Good Faith 88](#_Toc300749302)

[**H. Settlement of Disputes** 88](#_Toc300749303)

[44. Amicable Settlement 88](#_Toc300749304)

[45.Dispute Resolution 88](#_Toc300749305)

[**Attachment 1: Bank’s Policy – Corrupt and Fraudulent Practices** 89](#_Toc300749306)

[**III.Special Conditions of Contract** 91](#_Toc300749307)

[**IV.Appendices** 97](#_Toc300749308)

[Appendix A – Terms of Reference 97](#_Toc300749309)

[Appendix B - Key Experts 97](#_Toc300749310)

[Appendix C – Breakdown of Contract Price 97](#_Toc300749311)

[Appendix D - Form of Advance Payments Guarantee 101](#_Toc300749312)

# Preface

1. The standard Contract form consists of four parts: the Form of Contract to be signed by the Client and the Consultant, the General Conditions of Contract (GCC), including Attachment 1 (Bank’s Policy – Corrupt and Fraudulent Practices); the Special Conditions of Contract (SCC); and the Appendices.
2. The General Conditions of Contract, including Attachment 1, shall not be modified. The Special Conditions of Contract that contain clauses specific to each Contract intend to supplement, but not over-write or otherwise contradict, the General Conditions.

**Contract for Consultant’s Services**

**Lump-Sum**

**Project Name: Advanced Draft Benefit Sharing Plan**

**Contract No. NEP-REDD-64749-CS-QCBS**

**between**

REDD Implementation Center

**and**

*[****Name of the Consultant****]*

**Dated:**

# Form of Contract

**Lump-Sum**

(Text in brackets [ ] is optional; all notes should be deleted in the final text)

This CONTRACT (hereinafter called the “Contract”) is made the *[number]* day of the month of *[month]*, *[year]*, between, on the one hand, *[name of Client or Recipient]* (hereinafter called the “Client”) and, on the other hand, *[name of Consultant]* (hereinafter called the “Consultant”).

*[If the Consultant consist of more than one entity, the above should be partially amended to read as follows:* “…(hereinafter called the “Client”) and, on the other hand, a Joint Venture (name of the JV) consisting of the following entities, each member of which will be jointly and severally liable to the Client for all the Consultant’s obligations under this Contract, namely, *[name of member]* and *[name of member]* (hereinafter called the “Consultant”).]

WHEREAS

(a) the Client has requested the Consultant to provide certain consulting services as defined in this Contract (hereinafter called the “Services”);

(b) the Consultant, having represented to the Client that it has the required professional skills, expertise and technical resources, has agreed to provide the Services on the terms and conditions set forth in this Contract;

(c) the Client has received [*or* has applied for] a loan [*or* credit *or* grant] from the [*insert as relevant, International Bank for Reconstruction and Development (IBRD) or International Development Association (IDA)]:*toward the cost of the Services and intends to apply a portion of the proceeds of this [loan/credit/grant] to eligible payments under this Contract, it being understood that (i) payments by the Bank will be made only at the request of the Client and upon approval by the Bank; (ii) such payments will be subject, in all respects, to the terms and conditions of the [loan/financing/grant]agreement, including prohibitions of withdrawal from the [loan/credit/grant] account for the purpose of any payment to persons or entities, or for any import of goods, if such payment or import, to the knowledge of the Bank, is prohibited by the decision of the United Nations Security council taken under Chapter VII of the Charter of the United Nations; and (iii) no party other than the Client shall derive any rights from the [loan/financing/grant] agreement or have any claim to the [loan/credit/grant] proceeds;

NOW THEREFORE the parties hereto hereby agree as follows:

1. The following documents attached hereto shall be deemed to form an integral part of this Contract:

(a) The General Conditions of Contract(including Attachment 1 “Bank Policy – Corrupt and Fraudulent Practices);

(b) The Special Conditions of Contract;

(c) Appendices:

Appendix A: Terms of Reference

Appendix B: Key Experts

Appendix C: Breakdown of Contract Price

Appendix D: Form of Advance Payments Guarantee

In the event of any inconsistency between the documents, the following order of precedence shall prevail: the Special Conditions of Contract; the General Conditions of Contract, including Attachment 1; Appendix A; Appendix B; Appendix C; Appendix D. Any reference to this Contract shall include, where the context permits, a reference to its Appendices.

2. The mutual rights and obligations of the Client and the Consultant shall be as set forth in the Contract, in particular:

(a) the Consultant shall carry out the Services in accordance with the provisions of the Contract; and

(b) the Client shall make payments to the Consultant in accordance with the provisions of the Contract.

IN WITNESS WHEREOF, the Parties hereto have caused this Contract to be signed in their respective names as of the day and year first above written.

For and on behalf of *[Name of Client]*

*[Authorized Representative of the Client – name, title and signature]*

For and on behalf of *[Name of Consultant or Name of a Joint Venture]*

*[Authorized Representative of the Consultant – name and signature]*

*[For a joint venture, either all members shall sign or only the lead member, in which case the power of attorney to sign on behalf of all members shall be attached.*

For and on behalf of each of the members of the Consultant *[insert the Name of the Joint Venture]*

*[Name of the lead member]*

*[Authorized Representative on behalf of a Joint Venture]*

*[add signature blocks for each member if all are signing]*

# General Conditions of Contract

# A. General Provisions

|  |  |
| --- | --- |
| 1. Definitions | * 1. Unless the context otherwise requires, the following terms whenever used in this Contract have the following meanings:  1. “Applicable Guidelines” means Guidelines for Selection and Employment of Consultants under IBRD Loans and IDA Credits & Grants by World Bank Borrowers, dated January 2011. 2. “Applicable Law” means the laws and any other instruments having the force of law in the Client’s country, or in such other country as may be specified in the **Special Conditions of Contract (SCC)**, as they may be issued and in force from time to time. 3. “Bank” means the International Bank for Reconstruction and Development (IBRD) or the International Development Association (IDA). 4. “Borrower” means the Government, Government agency or other entity thatsigns the financing agreementwith the Bank. 5. “Client” means the implementing agency that signs the Contract for the Services with the Selected Consultant. 6. “Consultant” means a legally-established professional consulting firm or entity selected by the Client to provide the Services under the signed Contract. 7. “Contract” means the legally binding written agreement signed between the Client and the Consultant and which includes all the attached documents listed in its paragraph 1 of the Form of Contract (the General Conditions (GCC), the Special Conditions (SCC), and the Appendices). 8. “Day” means a working day unless indicated otherwise. 9. “Effective Date” means the date on which this Contract comes into force and effect pursuant to Clause GCC 11. 10. “Experts” means, collectively, Key Experts, Non-Key Experts, or any other personnel of the Consultant, Sub-consultant or JV member(s) assigned by the Consultant to perform the Services or any part thereof under the Contract. 11. “Foreign Currency” means any currency other than the currency of the Client’s country. 12. “GCC” means these General Conditions of Contract. 13. “Government” means the government of the Client’s country. 14. “Joint Venture (JV)” means an associationwith or without a legal personality distinct from that of its members, of more than one entity where one member has the authority to conduct all businesses for and on behalf of any and all the members of the JV, and where the members of the JV are jointly and severally liable to the Client for the performance of the Contract. 15. “Key Expert(s)” means an individual professional whose skills, qualifications, knowledge and experience are critical to the performance of the Services under the Contract and whose Curricula Vitae (CV) was taken into account in the technical evaluation of the Consultant’s proposal. 16. “Local Currency” means the currency of the Client’s country. 17. “Non-Key Expert(s)” means an individual professional provided by the Consultant or its Sub-consultant to perform the Services or any part thereof under the Contract. 18. “Party” means the Client or the Consultant, as the case may be, and “Parties” means both of them. 19. “SCC” means the Special Conditions of Contract by which the GCC may be amended or supplemented but not over-written. 20. “Services” means the work to be performed by the Consultant pursuant to this Contract, as described in Appendix A hereto. 21. “Sub-consultants” means an entity to whom/which the Consultant subcontracts any part of the Services while remaining solely liable for the execution of the Contract. 22. “Third Party” means any person or entity other than the Government, the Client, the Consultant or a Sub-consultant. |
| Relationship between the Parties | * 1. Nothing contained herein shall be construed as establishing a relationship of master and servant or of principal and agent as between the Client and the Consultant. The Consultant, subject to this Contract, has complete charge of the Experts and Sub-consultants, if any, performing the Services and shall be fully responsible for the Services performed by them or on their behalf hereunder. |
| Law Governing Contract | * 1. This Contract, its meaning and interpretation, and the relation between the Parties shall be governed by the Applicable Law. |
| Language | * 1. This Contract has been executed in the language specified in the **SCC**, which shall be the binding and controlling language for all matters relating to the meaning or interpretation of this Contract. |
| Headings | * 1. The headings shall not limit, alter or affect the meaning of this Contract. |
| Communications | * 1. Any communication required or permitted to be given or made pursuant to this Contract shall be in writing in the language specified in Clause GCC 4. Any such notice, request or consent shall be deemed to have been given or made when delivered in person to an authorized representative of the Party to whom the communication is addressed, or when sent to such Party at the address specified in the **SCC**.   2. A Party may change its address for notice hereunder by giving the other Party any communication of such change to the address specified in the **SCC**. |
| Location | * 1. The Services shall be performed at such locations as are specified in **Appendix A** hereto and, where the location of a particular task is not so specified, at such locations, whether in the Government’s country or elsewhere, as the Client may approve. |
| Authority of Member in Charge | * 1. In case the Consultant is a Joint Venture, the members hereby authorize the member specified in the **SCC** to act on their behalf in exercising all the Consultant’s rights and obligations towards the Client under this Contract, including without limitation the receiving of instructions and payments from the Client. |
| Authorized Representatives | * 1. Any action required or permitted to be taken, and any document required or permitted to be executed under this Contract by the Client or the Consultant may be taken or executed by the officials specified in the **SCC.** |
| Corrupt and Fraudulent Practices | * 1. The Bank requires compliance with its policy in regard to corrupt and fraudulentpractices as set forth in **Attachment 1** to the GCC. |
| a. Commissions and Fees | * 1. The Client requires the Consultant to disclose any commissions, gratuities or fees that may have been paid or are to be paid to agents or any other party with respect to the selection process or execution of the Contract. The information disclosed must include at least the name and address of the agent or other party, the amount and currency, and the purpose of the commission, gratuity or fee. Failure to disclose such commissions, gratuities or fees may result in termination of the Contract and/or sanctions by the Bank. |

# B. Commencement, Completion, Modification and Termination of Contract

|  |  |
| --- | --- |
| Effectiveness of Contract | * 1. This Contract shall come into force and effect on the date (the “Effective Date”) of the Client’s notice to the Consultant instructing the Consultant to begin carrying out the Services. This notice shall confirm that the effectiveness conditions, if any, listed in the **SCC** have been met. |
| Termination of Contract for Failure to Become Effective | * 1. If this Contract has not become effective within such time period after the date of Contract signature as specified in the **SCC**, either Party may, by not less than twenty two (22) days written notice to the other Party, declare this Contract to be null and void, and in the event of such a declaration by either Party, neither Party shall have any claim against the other Party with respect hereto. |
| Commencement of Services | * 1. The Consultant shall confirm availability of Key Experts and begin carrying out the Services not later than the number of days after the Effective Date specified in the **SCC**. |
| Expiration of Contract | * 1. Unless terminated earlier pursuant to Clause GCC 19 hereof, this Contract shall expire at the end of such time period after the Effective Date as specified in the **SCC**. |
| Entire Agreement | * 1. This Contract contains all covenants, stipulations and provisions agreed by the Parties. No agent or representative of either Party has authority to make, and the Parties shall not be bound by or be liable for, any statement, representation, promise or agreement not set forth herein. |
| Modifications or Variations | * 1. Any modification or variation of the terms and conditions of this Contract, including any modification or variation of the scope of the Services, may only be made by written agreement between the Parties. However, each Party shall give due consideration to any proposals for modification or variation made by the other Party.   2. In cases of substantial modifications or variations, the prior written consent of the Bank is required. |
| Force Majeure |  |
| a. Definition | * 1. For the purposes of this Contract, “Force Majeure” means an event which is beyond the reasonable control of a Party, is not foreseeable, is unavoidable, and makes a Party’s performance of its obligations hereunder impossible or so impractical as reasonably to be considered impossible under the circumstances, and subject to those requirements, includes, but is not limited to, war, riots, civil disorder, earthquake, fire, explosion, storm, flood or other adverse weather conditions, strikes, lockouts or other industrial action confiscation or any other action by Government agencies.   2. Force Majeure shall not include (i) any event which is caused by the negligence or intentional action of a Party or such Party’s Experts, Sub-consultants or agents or employees, nor (ii) any event which a diligent Party could reasonably have been expected to both take into account at the time of the conclusion of this Contract, and avoid or overcome in the carrying out of its obligations hereunder.   3. Force Majeure shall not include insufficiency of funds or failure to make any payment required hereunder. |
| b. No Breach of Contract | * 1. The failure of a Party to fulfill any of its obligations hereunder shall not be considered to be a breach of, or default under, this Contract insofar as such inability arises from an event of Force Majeure, provided that the Party affected by such an event has taken all reasonable precautions, due care and reasonable alternative measures, all with the objective of carrying out the terms and conditions of this Contract. |
| c. Measures to be Taken | * 1. A Party affected by an event of Force Majeure shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall take all reasonable measures to minimize the consequences of any event of Force Majeure.   2. A Party affected by an event of Force Majeure shall notify the other Party of such event as soon as possible, and in any case not later than fourteen (14) calendar days following the occurrence of such event, providing evidence of the nature and cause of such event, and shall similarly give written notice of the restoration of normal conditions as soon as possible.   3. Any period within which a Party shall, pursuant to this Contract, complete any action or task, shall be extended for a period equal to the time during which such Party was unable to perform such action as a result of Force Majeure.   4. During the period of their inability to perform the Services as a result of an event of Force Majeure, the Consultant, upon instructions by the Client, shall either:   (a) demobilize, in which case the Consultant shall be reimbursed for additional costs they reasonably and necessarily incurred, and, if required by the Client, in reactivating the Services; or  (b) continue with the Services to the extent reasonably possible, in which case the Consultant shall continue to be paid under the terms of this Contract and be reimbursed for additional costs reasonably and necessarily incurred.   * 1. In the case of disagreement between the Parties as to the existence or extent of Force Majeure, the matter shall be settled according to Clauses GCC 44& 45. |
| Suspension | * 1. The Client may, by written notice of suspension to the Consultant, suspend all payments to the Consultant hereunder if the Consultant fails to perform any of its obligations under this Contract, including the carrying out of the Services, provided that such notice of suspension (i) shall specify the nature of the failure, and (ii) shall request the Consultant to remedy such failure within a period not exceeding thirty (30) calendar days after receipt by the Consultant of such notice of suspension. |
| Termination | 19.1. This Contract may be terminated by either Party as per provisions set up below: |
| a. By the Client | 19.1.1. The Client may terminate this Contract in case of the occurrence of any of the events specified in paragraphs (a) through (f) of this Clause. In such an occurrence the Client shall give at least thirty (30) calendar days’ written notice of termination to the Consultant in case of the events referred to in (a) through (d); at least sixty (60) calendar days’ written notice in case of the event referred to in (e); and at least five (5) calendar days’ written notice in case of the event referred to in (f):  (a) If the Consultant fails to remedy a failure in the performance of its obligations hereunder, as specified in a notice of suspension pursuant to Clause GCC 18;  (b) If the Consultant becomes (or, if the Consultant consists of more than one entity, if any of its members becomes) insolvent or bankrupt or enter into any agreements with their creditors for relief of debt or take advantage of any law for the benefit of debtors or go into liquidation or receivership whether compulsory or voluntary;  (c) If the Consultant fails to comply with any final decision reached as a result of arbitration proceedings pursuant to Clause GCC 45.1;  (d) If, as the result of Force Majeure, the Consultant is unable to perform a material portion of the Services for a period of not less than sixty (60) calendar days;  (e) If the Client, in its sole discretion and for any reason whatsoever, decides to terminate this Contract;  (f) If the Consultant fails to confirm availability of Key Experts as required in Clause GCC 13.  19.1.2. Furthermore, if the Client determines that the Consultant has engaged in corrupt, fraudulent, collusive, coercive or obstructive practices, in competing for or in executing the Contract, then the Client may, after giving fourteen (14) calendar days written notice to the Consultant, terminate the Consultant's employment under the Contract. |
| b. By the Consultant | 19.1.3. The Consultant may terminate this Contract, by not less than thirty (30) calendar days’ written notice to the Client, in case of the occurrence of any of the events specified in paragraphs (a) through (d) of this Clause.  (a) If the Client fails to pay any money due to the Consultant pursuant to this Contract and not subject to dispute pursuant to Clause GCC 45.1 within forty-five (45) calendar days after receiving written notice from the Consultant that such payment is overdue.  (b) If, as the result of Force Majeure, the Consultant is unable to perform a material portion of the Services for a period of not less than sixty (60) calendar days.  (c) If the Client fails to comply with any final decision reached as a result of arbitration pursuant to Clause GCC 45.1.  (d) If the Client is in material breach of its obligations pursuant to this Contract and has not remedied the same within forty-five (45) days (or such longer period as the Consultant may have subsequently approved in writing) following the receipt by the Client of the Consultant’s notice specifying such breach. |
| c. Cessation of Rights and Obligations | 19.1.4. Upon termination of this Contract pursuant to Clauses GCC 12 or GCC 19 hereof, or upon expiration of this Contract pursuant to Clause GCC 14, all rights and obligations of the Parties hereunder shall cease, except (i) such rights and obligations as may have accrued on the date of termination or expiration, (ii) the obligation of confidentiality set forth in Clause GCC 22, (iii) the Consultant’s obligation to permit inspection, copying and auditing of their accounts and records set forth in Clause GCC 25, and (iv) any right which a Party may have under the Applicable Law. |
| d. Cessation of Services | 19.1.5. Upon termination of this Contract by notice of either Party to the other pursuant to Clauses GCC 19a or GCC 19b, the Consultant shall, immediately upon dispatch or receipt of such notice, take all necessary steps to bring the Services to a close in a prompt and orderly manner and shall make every reasonable effort to keep expenditures for this purpose to a minimum. With respect to documents prepared by the Consultant and equipment and materials furnished by the Client, the Consultant shall proceed as provided, respectively, by Clauses GCC 27 or GCC 28. |
| e. Payment upon Termination | 19.1.6. Upon termination of this Contract, the Client shall make the following payments to the Consultant:  (a) payment for Services satisfactorily performed prior to the effective date of termination; and  (b) in the case of termination pursuant to paragraphs (d) and (e) of Clause GCC19.1.1, reimbursement of any reasonable cost incidental to the prompt and orderly termination of this Contract, including the cost of the return travel of the Experts. |

# C. Obligations of the Consultant

|  |  |
| --- | --- |
| General |  |
| a. Standard of Performance | 20.1 The Consultant shall perform the Services and carry out the Services with all due diligence, efficiency and economy, in accordance with generally accepted professional standards and practices, and shall observe sound management practices, and employ appropriate technology and safe and effective equipment, machinery, materials and methods. The Consultant shall always act, in respect of any matter relating to this Contract or to the Services, as a faithful adviser to the Client, and shall at all times support and safeguard the Client’s legitimate interests in any dealings with the third parties.  20.2. The Consultant shall employ and provide such qualified and experienced Experts and Sub-consultants as are required to carry out the Services.  20.3. The Consultant may subcontract part of the Services to an extent and with such Key Experts and Sub-consultants as may be approved in advance by the Client. Notwithstanding such approval, the Consultant shall retain full responsibility for the Services. |
| b. Law Applicable to Services | 20.4. The Consultant shall perform the Services in accordance with the Contract and the Applicable Law and shall take all practicable steps to ensure that any of its Experts and Sub-consultants, comply with the Applicable Law.  20.5. Throughout the execution of the Contract, the Consultant shall comply with the import of goods and services prohibitions in the Client’s country when  (a) as a matter of law or official regulations, the Borrower’s country prohibits commercial relations with that country; or  (b) by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s Country prohibits any import of goods from that country or any payments to any country, person, or entity in that country.  20.6. The Client shall notify the Consultant in writing of relevant local customs, and the Consultant shall, after such notification, respect such customs. |
| Conflict of Interests | 21.1. The Consultant shall hold the Client’s interests paramount, without any consideration for future work, and strictly avoid conflict with other assignments or their own corporate interests. |
| a. Consultant Not to Benefit from Commissions,Discounts, etc. | 21.1.1 The payment of the Consultant pursuant to GCC F (Clauses GCC 38 through 42) shall constitute the Consultant’s only payment in connection with this Contract and, subject to Clause GCC 21.1.3, the Consultant shall not accept for its own benefit any trade commission, discount or similar payment in connection with activities pursuant to this Contract or in the discharge of its obligations hereunder, and the Consultant shall use its best efforts to ensure that any Sub-consultants, as well as the Experts and agents of either of them, similarly shall not receive any such additional payment.  21.1.2 Furthermore, if the Consultant, as part of the Services, has the responsibility of advising the Client on the procurement of goods, works or services, the Consultant shall comply with the Bank’s Applicable Guidelines, and shall at all times exercise such responsibility in the best interest of the Client. Any discounts or commissions obtained by the Consultant in the exercise of such procurement responsibility shall be for the account of the Client. |
| b. Consultant and Affiliates Not to Engage in Certain Activities | 21.1.3 The Consultant agrees that, during the term of this Contract and after its termination, the Consultant and any entity affiliated with the Consultant, as well as any Sub-consultants and any entity affiliated with such Sub-consultants, shall be disqualified from providing goods, works or non-consultingservices resulting from or directly related to the Consultant’s Services for the preparation or implementation of the project, unless otherwise indicated in the **SCC**. |
| c. Prohibition of Conflicting Activities | 21.1.4 The Consultant shall not engage, and shall cause its Experts as well as its Sub-consultants not to engage, either directly or indirectly, in any business or professional activities that would conflict with the activities assigned to them under this Contract. |
| d. Strict Duty to Disclose Conflicting Activities | 21.1.5 The Consultant has an obligation and shall ensure that its Experts and Sub-consultants shall have an obligation to disclose any situation of actual or potential conflict that impacts their capacity to serve the best interest of their Client, or that may reasonably be perceived as having this effect. Failure to disclose said situations may lead to the disqualification of the Consultant or the termination of its Contract. |
| Confidentiality | 22.1 Except with the prior written consent of the Client, the Consultant and the Experts shall not at any time communicate to any person or entity any confidential information acquired in the course of the Services, nor shall the Consultant and the Experts make public the recommendations formulated in the course of, or as a result of, the Services. |
| Liability of the Consultant | 23.1 Subject to additional provisions, if any, set forth in the **SCC**, the Consultant’s liability under this Contract shall be provided by the Applicable Law. |
| Insurance to be Taken out by the Consultant | 24.1 The Consultant (i) shall take out and maintain, and shall cause any Sub-consultants to take out and maintain, at its (or the Sub-consultants’, as the case may be) own cost but on terms and conditions approved by the Client, insurance against the risks, and for the coverage specified in the **SCC,** and (ii) at the Client’s request, shall provide evidence to the Client showing that such insurance has been taken out and maintained and that the current premiums therefore have been paid. The Consultant shall ensure that such insurance is in place prior to commencing the Services as stated in Clause GCC 13. |
| Accounting, Inspection and Auditing | 25.1 The Consultant shall keep, and shall make all reasonable efforts to cause its Sub-consultants to keep, accurate and systematic accounts and records in respect of the Services and in such form and detail as will clearly identify relevant time changes and costs.  25.2 The Consultant shall permit and shall cause its Sub-consultants to permit, the Bank and/or persons appointed by the Bank to inspect the Site and/or all accounts and records relating to the performance of the Contract and the submission of the Proposal to provide the Services, and to have such accounts and records audited by auditors appointed by the Bank if requested by the Bank. The Consultant’s attention is drawn to Clause GCC 10 which provides, inter alia, that acts intended to materially impede the exercise of the Bank’s inspection and audit rights provided for under this Clause GCC25.2 constitute a prohibited practice subject to contract termination (as well as to a determination of ineligibility under the Bank’s prevailing sanctions procedures.) |
| Reporting Obligations | 26.1 The Consultant shall submit to the Client the reports and documents specified in **Appendix A**, in the form, in the numbers and within the time periods set forth in the said Appendix. |
| Proprietary Rights of the Client in Reports and Records | 27.1 Unless otherwise indicated in the **SCC**, all reports and relevant data and information such as maps, diagrams, plans, databases, other documents and software, supporting records or material compiled or prepared by the Consultant for the Client in the course of the Services shall be confidential and become and remain the absolute property of the Client. The Consultant shall, not later than upon termination or expiration of this Contract, deliver all such documents to the Client, together with a detailed inventory thereof. The Consultant may retain a copy of such documents, data and/or software but shall not use the same for purposes unrelated to this Contract without prior written approval of the Client.  27.2 If license agreements are necessary or appropriate between the Consultant and third parties for purposes of development of the plans, drawings, specifications, designs, databases, other documents and software, the Consultant shall obtain the Client’s prior written approval to such agreements, and the Client shall be entitled at its discretion to require recovering the expenses related to the development of the program(s) concerned. Other restrictions about the future use of these documents and software, if any, shall be specified in the **SCC**. |
| Equipment, Vehicles and Materials | 28.1 Equipment, vehicles and materials made available to the Consultant by the Client, or purchased by the Consultant wholly or partly with funds provided by the Client, shall be the property of the Client and shall be marked accordingly. Upon termination or expiration of this Contract, the Consultant shall make available to the Client an inventory of such equipment, vehicles and materials and shall dispose of such equipment, vehicles and materials in accordance with the Client’s instructions. While in possession of such equipment, vehicles and materials, the Consultant, unless otherwise instructed by the Client in writing, shall insure them at the expense of the Client in an amount equal to their full replacement value.  28.2 Any equipment or materials brought by the Consultant or its Experts into the Client’s country for the use either for the project or personal use shall remain the property of the Consultant or the Experts concerned, as applicable. |

# D. Consultant’s Experts andSub-Consultants

|  |  |
| --- | --- |
| Description of Key Experts | 29.1 The title, agreed job description, minimum qualification and estimated period of engagement to carry out the Services of each of the Consultant’s Key Experts are described in **Appendix B.** |
| Replacement of Key Experts | 30.1 Except as the Client may otherwise agree in writing, no changes shall be made in the Key Experts.  30.2 Notwithstanding the above, the substitution of Key Experts during Contract execution may be considered only based on the Consultant’s written request and due to circumstances outside the reasonable control of the Consultant, including but not limited to death or medical incapacity. In such case, the Consultant shall forthwith provide as a replacement, a person of equivalent or better qualifications and experience, and at the same rate of remuneration. |
| Removal of Experts or Sub-consultants | 31.1 If the Client finds that any of the Experts or Sub-consultant has committed serious misconduct or has been charged with having committed a criminal action, or shall the Client determine that Consultant’s Expert of Sub-consultant have engaged in corrupt, fraudulent, collusive, coercive or obstructive practice while performing the Services, the Consultant shall, at the Client’s written request, provide a replacement.  31.2 In the event that any of Key Experts, Non-Key Experts or Sub-consultants is found by the Client to be incompetent or incapable in discharging assigned duties, the Client, specifying the grounds therefore, may request the Consultant to provide a replacement.  31.3 Any replacement of the removed Experts or Sub-consultants shall possess better qualifications and experience and shall be acceptable to the Client.  31.4 The Consultant shall bear all costs arising out of or incidental to any removal and/or replacement of such Experts. |

# E. Obligations of the Client

|  |  |  |
| --- | --- | --- |
| Assistance and Exemptions | 32.1 Unless otherwise specified in the **SCC**, the Client shall use its best efforts to:  (a) Assist the Consultant with obtaining work permits and such other documents as shall be necessary to enable the Consultant to perform the Services.  (b) Assist the Consultant with promptly obtaining, for the Experts and, if appropriate, their eligible dependents, all necessary entry and exit visas, residence permits, exchange permits and any other documents required for their stay in the Client’s country while carrying out the Services under the Contract.  (c) Facilitate prompt clearance through customs of any property required for the Services and of the personal effects of the Experts and their eligible dependents.  (c) Issue to officials, agents and representatives of the Government all such instructions and information as may be necessary or appropriate for the prompt and effective implementation of the Services.  (d) Assist the Consultant and the Experts and any Sub-consultants employed by the Consultant for the Services with obtaining exemption from any requirement to register or obtain any permit to practice their profession or to establish themselves either individually or as a corporate entity in the Client’s country according to the applicable law in the Client’s country.  (e) Assist the Consultant, any Sub-consultants and the Experts of either of them with obtaining the privilege, pursuant to the applicable law in the Client’s country, of bringing into the Client’s country reasonable amounts of foreign currency for the purposes of the Services or for the personal use of the Experts and of withdrawing any such amounts as may be earned therein by the Experts in the execution of the Services.  (f) Provide to the Consultant any such other assistance as may be specified in the **SCC**. | |
| Access to Project Site | 33.1 The Client warrants that the Consultant shall have, free of charge, unimpeded access to the project site in respect of which access is required for the performance of the Services. The Client will be responsible for any damage to the project site or any property thereon resulting from such access and will indemnify the Consultant and each of the experts in respect of liability for any such damage, unless such damage is caused by the willful default or negligence of the Consultant or any Sub-consultants or the Experts of either of them. | |
| Change in the Applicable Law Related to Taxes and Duties | 34.1 If, after the date of this Contract, there is any change in the applicable law in the Client’s country with respect to taxes and duties which increases or decreases the cost incurred by the Consultant in performing the Services, then the remuneration and reimbursable expenses otherwise payable to the Consultant under this Contract shall be increased or decreased accordingly by agreement between the Parties hereto, and corresponding adjustments shall be made to the Contract price amount specified in Clause GCC 38.1 | |
| Services, Facilities and Property of the Client | 35.1 The Client shall make available to the Consultant and the Experts, for the purposes of the Services and free of any charge, the services, facilities and property described in the Terms of Reference (**Appendix A)** at the times and in the manner specified in said **Appendix A.** | |
| Counterpart Personnel | 36.1 The Client shall make available to the Consultant free of charge such professional and support counterpart personnel, to be nominated by the Client with the Consultant’s advice, if specified in **Appendix A**.  36.2 Professional and support counterpart personnel, excluding Client’s liaison personnel, shall work under the exclusive direction of the Consultant. If any member of the counterpart personnel fails to perform adequately any work assigned to such member by the Consultant that is consistent with the position occupied by such member, the Consultant may request the replacement of such member, and the Client shall not unreasonably refuse to act upon such request. |
| Payment Obligation | 37.1 In consideration of the Services performed by the Consultant under this Contract, the Client shall make such payments to the Consultant for the deliverables specified in **Appendix A** and in such manner as is provided by GCC F below. | |

# F. Payments to the Consultant

|  |  |
| --- | --- |
| Contract Price | 38.1 The Contract price is fixed and is set forth in the **SCC.** The Contract price breakdown is provided in **Appendix C**.  38.2 Any change to the Contract price specified in Clause 38.1 can be made only if the Parties have agreed to the revised scope of Services pursuant to Clause GCC 16 and have amended in writing the Terms of Reference in **Appendix A**. |
| Taxes and Duties | 39.1 The Consultant, Sub-consultants and Experts are responsible for meeting any and all tax liabilities arising out of the Contract unless it is stated otherwise in the **SCC**.  39.2 As an exception to the above and as stated in the **SCC**, all local identifiable indirect taxes (itemized and finalized at Contract negotiations) are reimbursed to the Consultant or are paid by the Client on behalf of the Consultant. |
| Currency of Payment | 40.1 Any payment under this Contract shall be made in the currency(ies) of the Contract. |
| Mode of Billing and Payment | 41.1 The total payments under this Contract shall not exceed the Contract price set forth in Clause GCC 38.1.  41.2 The payments under this Contract shall be made in lump-sum installments against deliverables specified in **Appendix A**. The payments will be made according to the payment schedule stated in the **SCC**.  41.2.1 *Advance payment:* Unless otherwise indicated in the **SCC**, an advance payment shall be made against an advance payment bank guarantee acceptable to the Client in an amount (or amounts) and in a currency (or currencies) specified in the **SCC**. Such guarantee (i) is to remain effective until the advance payment has been fully set off, and (ii) is to be in the form set forth in **Appendix D**, or in such other form as the Client shall have approved in writing. The advance payments will be set off by the Client in equal portions against the lump-sum installments specified in the **SCC** until said advance payments have been fully set off.  41.2.2 *The Lump-Sum Installment Payments.* The Client shall pay the Consultant within sixty (60) days after the receipt by the Client of the deliverable(s) and the cover invoice for the related lump-sum installment payment. The payment can be withheld if the Client does not approve the submitted deliverable(s) as satisfactory in which case the Client shall provide comments to the Consultant within the same sixty (60) days period. The Consultant shall thereupon promptly make any necessary corrections, and thereafter the foregoing process shall be repeated.  41.2.3 *The Final Payment* .The final payment under this Clause shall be made only after the final report l have been submitted by the Consultant and approved as satisfactory by the Client. The Services shall then be deemed completed and finally accepted by the Client. The last lump-sum installment shall be deemed approved for payment by the Client within ninety (90) calendar days after receipt of the final report by the Client unless the Client, within such ninety (90) calendar day period, gives written notice to the Consultant specifying in detail deficiencies in the Services, the final report. The Consultant shall thereupon promptly make any necessary corrections, and thereafter the foregoing process shall be repeated. 41.2.4 All payments under this Contract shall be made to the accounts of the Consultant specified in the **SCC**.  41.2.4 With the exception of the final payment under 41.2.3 above, payments do not constitute acceptance of the whole Services nor relieve the Consultant of any obligations hereunder. |
| Interest on Delayed Payments | 42.1 If the Client had delayed payments beyond fifteen (15) days after the due date stated in Clause GCC 41.2.2 , interest shall be paid to the Consultant on any amount due by, not paid on, such due date for each day of delay at the annual rate stated in the **SCC.** |

# G. Fairness and Good Faith

|  |  |
| --- | --- |
| Good Faith | 43.1 The Parties undertake to act in good faith with respect to each other’s rights under this Contract and to adopt all reasonable measures to ensure the realization of the objectives of this Contract. |

# H. Settlement of Disputes

|  |  |
| --- | --- |
| Amicable Settlement | 44.1 The Parties shall seek to resolve any dispute amicably by mutual consultation.  44.2 If either Party objects to any action or inaction of the other Party, the objecting Party may file a written Notice of Dispute to the other Party providing in detail the basis of the dispute. The Party receiving the Notice of Dispute will consider it and respond in writing within fourteen (14) days after receipt. If that Party fails to respond within fourteen (14) days, or the dispute cannot be amicably settled within fourteen (14) days following the response of that Party, Clause GCC 45.1 shall apply. |
| Dispute Resolution | 45.1 Any dispute between the Parties arising under or related to this Contract that cannot be settled amicably may be referred to by either Party to the adjudication/arbitration in accordance with the provisions specified in the **SCC**. |

**II. General Conditions**

# Attachment 1: Bank’s Policy – Corrupt and Fraudulent Practices

(the text in this Attachment 1 shall not be modified)

**Guidelines for Selection and Employment of Consultants under IBRD Loans and IDA Credits & Grants by World Bank Borrowers, dated January 2011:**

“**Fraud and Corruption**

1.23 It is the Bank’s policy to require that Borrowers (including beneficiaries of Bank loans), consultants, and their agents (whether declared or not), sub-contractors, sub-consultants, service providers, or suppliers, and any personnel thereof, observe the highest standard of ethics during the selection and execution of Bank-financed contracts [footnote: In this context, any action taken by a consultant or any of its personnel, or its agents, or its sub-consultants, sub-contractors, services providers, suppliers, and/or their employees, to influence the selection process or contract execution for undue advantage is improper.]. In pursuance of this policy, the Bank:

(a) defines, for the purposes of this provision, the terms set forth below as follows:

1. “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party[[8]](#footnote-8);
2. “fraudulent practice” is any act or omission, including misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial or other benefit or to avoid an obligation[[9]](#footnote-9);
3. “collusive practices” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party[[10]](#footnote-10);
4. “coercive practices” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party[[11]](#footnote-11);
5. “obstructive practice” is

(aa) deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive, or collusive practice; and/or threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or

(bb) acts intended to materially impede the exercise of the Bank’s inspection and audit rights;

(b) will reject a proposal for award if it determines that the consultant recommended for award or any of its personnel, or its agents, or its sub-consultants, sub-contractors, services providers, suppliers, and/or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;

(c) will declare misprocurement and cancel the portion of the Loan allocated to a contract if it determines at any time that representatives of the Borrower or of a recipient of any part of the proceeds of the Loan were engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the selection process or the implementation of the contract in question, without the Borrower having taken timely and appropriate action satisfactory to the Bank to address such practices when they occur, including by failing to inform the Bank in a timely manner they knew of the practices;

(d) will sanction a firm or an individual at any time, in accordance with prevailing Bank’s sanctions procedures[[12]](#footnote-12), including by publicly declaring such firm or an ineligible, either indefinitely or for a stated period of time: (i) to be awarded a Bank-financed contract, and (ii) to be a nominated[[13]](#footnote-13) sub-consultant, supplier, or service provider of an otherwise eligible firm being awarded a Bank-financed contract.

# Special Conditions of Contract

|  |  |
| --- | --- |
| **Number of GC Clause** | **Amendments of, and Supplements to, Clauses in the General Conditions of Contract** |
| **1.1(b) and 3.1** | **The Contract shall be construed in accordance with the law of** Nepal |
| **4.1** | **The language is: English** |
| **6.1 and 6.2** | **The addresses are:**  Client : REDD IC, Babarmahal    Attention : Chief, REDD IC  Facsimile : 977-1-4215261  E-mail (where permitted):info@redd.gov.np  Consultant :    Attention :  Facsimile :  E-mail (where permitted) : |
| **8.1** | *[If the Consultant consists only of one entity, state “N/A”;*  *OR*  *If the Consultant is a Joint Venture consisting of more than one entity, the name of the JV member whose address is specified in Clause SCC6.1 should be inserted here. ]*  **The Lead Member on behalf of the JV is**\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*[insert name of the member]* |
| **9.1** | **The Authorized Representatives are:**  **For the Client:** *[name, title]*  **For the Consultant:** *[name, title]* |
| **11.1** | *“N/A”* |
| **12.1** | **Termination of Contract for Failure to Become Effective:**  **The time period shall be: one month** |
| **13.1** | **Commencement of Services:**  **The number of days shall be : 7 days**.  Confirmation of Key Experts’ availability to start the Assignment shall be submitted to the Client in writing as a written statement signed by each Key Expert. |
| **14.1** | **Expiration of Contract:**  **The time period shall be : 3 months**. |
| **21 b.** | **The Client reserves the right to determine on a case-by-case basis whether the Consultant should be disqualified from providing goods, works or non-consulting services due to a conflict of a nature described in Clause GCC 21.1.3**  Yes |

|  |  |
| --- | --- |
| **23.1** | **No additional provisions.** |
| **24.1** | **The insurance coverage against the risks shall be as follows:**  **(a) Professional liability insurance, with a minimum coverage of equivalent to Contract Amount***[insert amount and currency which should be not less than the total ceiling amount of the Contract]*;  (b) Rs.100,000.00Third Party motor vehicle liability insurance in respect of motor vehicles operated in the Client’s country by the Consultant or its Experts or Sub-consultants, with a minimum coverage of *Rs. NA*  (c) Rs.200,000.00Third Party liability insurance, with a minimum coverage of *Rs. NA*  (d) employer’s liability and workers’ compensation insurance in respect of the experts and Sub-consultants in accordance with the relevant provisions of the applicable law in the Client’s country, as well as, with respect to such Experts, any such life, health, accident, travel or other insurance as may be appropriate; and |
| **27.1** | *NA* |
| **27.2** | **The Consultant shall not use these *documents and software developed and produced during this assignment* for purposes unrelated to this Contract without the prior written approval of the Client**. |
| **32.1**  **(a) through (e)** | *[List here any changes or additions to Clause GCC 32.1. If there are no such changes or additions, delete this Clause SCC 321.]* |
| **32.1(f)** | *[List here any other assistance to be provided by the Client. If there is no such other assistance, delete this Clause SCC 32.1(f).]* |
| **38.1** | **The Contract price is:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[insert amount and currency for each currency as applicable] [indicate:* **inclusive** *or* **exclusive***]* **of local indirect taxes.**  **Any indirect local taxes chargeable in respect of this Contract for the Services provided by the Consultant shall** *[insert as appropriate: “***be paid***” or “***reimbursed***”]* **by the Client** *[insert as appropriate:”***for*“* or “to*”****]***the Consultant.**  **The amount of such taxes is \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ [insert the amount as finalized at the Contract’s negotiations on the basis of the estimates provided by the Consultant in Form FIN-2 of the Consultant’s Financial Proposal.** |
| **39.1 and 39.2** | The Consultant, Sub-consultants and Experts are responsible for meeting any and all tax liabilities arising out of the Contract. |
| **41.2** | **The payment schedule:**  **1st payment: 20% of contract price after submission of Inception Report and Approval by the Client.**  **2nd payment: 40% of Contract Price after submission of Draft report.**  **3rd Payment: 40% of Contract Price after submission of**  **Final Report accommodated and improved based on the feedback and suggestion in the consultation workshop.** |
| **41.2.1** | NA |
| **41.2.4** | **The accounts are:**  for foreign currency: *[insert account]*.  for local currency: *[insert account]*. |
| **42.1** | **The interest rate is**: *9%* |
| **45.1** | **Disputes shall be settled by arbitration in accordance with the following provisions:**  1. Selection of Arbitrators. Each dispute submitted by a Party to arbitration shall be heard by a sole arbitrator or an arbitration panel composed of three (3) arbitrators, in accordance with the following provisions:  (a) The Client and the Consultant shall attempt to settle amicably by direct negotiation any disagreement or dispute arising between them under or in connection with the Contract arbitrator for the matter in dispute.  (b) Any dispute between the Parties as to matters arising pursuant to this Contract which cannot be settled amicably within thirty (30) days after receipt by one Party of the other Party‘s request for such amicable settlement may be referred to Arbitration within 30 days after the expiration of amicable settlement period.  (c) In case of arbitration, the arbitration shall be conducted in accordance with the arbitration procedures published by the Nepal Council of Arbitration (NEPCA) at the place given in the SCC. |

# Appendices

Appendix A – Terms of Reference

………………………………………………………………………………………………

Appendix B - Key Experts

*[Insert a table based on Form TECH-6 of the Consultant’s Technical Proposal and finalized at the Contract’s negotiations. Attach the CVs (updated and signed by the respective Key Experts) demonstrating the qualifications of Key Experts.]*

……………………………………………………………………………………………………

Appendix C – Breakdown of Contract Price

*[Insert the table with the unit rates to arrive at the breakdown of the lump-sum price. The table shall be based on [Form FIN-3 and FIN-4] of the Consultant’s Proposal and reflect any changes agreed at the Contract negotiations, if any. The footnote shall list such changes made to [Form FIN-3 and FIN-4] at the negotiations or state that none has been made.]*

1. References in this SRFP to the “World Bank” or “Bank” include both the International Bank for Reconstruction and Development (IBRD) and International Development Association (IDA). [↑](#footnote-ref-1)
2. For the purpose of this sub-paragraph, “another party” refers to a public official acting in relation to the selection process or contract execution. In this context “public official” includes World Bank staff and employees of other organizations taking or reviewing selection decisions. [↑](#footnote-ref-2)
3. For the purpose of this sub-paragraph, “party” refers to a public official; the terms “benefit” and “obligation” relate to the selection process or contract execution; and the “act or omission” is intended to influence the selection process or contract execution. [↑](#footnote-ref-3)
4. For the purpose of this sub-paragraph, “parties” refers to participants in the procurement or selection process (including public officials) attempting either themselves, or through another person or entity not participating in the procurement or selection process, to simulate competition or to establish prices at artificial, non-competitive levels, or are privy to each other’s bid prices or other conditions. [↑](#footnote-ref-4)
5. For the purpose of this sub-paragraph, “party” refers to a participant in the selection process or contract execution. [↑](#footnote-ref-5)
6. A firm or an individual may be declared ineligible to be awarded a Bank-financed contract upon (i) completion of the Bank’s sanctions proceedings as per its sanctions procedures, including inter alia: cross-debarment as agreed with other International Financial Institutions, including Multilateral Development Banks, and through the application of the World Bank Group corporate administrative procurement sanctions procedures for fraud and corruption; and (ii) as a result of temporary suspension or early temporary suspension in connection with an ongoing sanctions proceedings. See footnote 12 and paragraph 8 of Appendix 1 of these Guidelines. [↑](#footnote-ref-6)
7. A nominated sub-consultant, supplier, or service provider is one which has been either (i) included by the consultant in its proposal because it brings specific and critical experience and know-how that are accounted for in the technical evaluation of the consultant’s proposal for the particular services; or (ii) appointed by the Borrower. [↑](#footnote-ref-7)
8. For the purpose of this sub-paragraph, “another party” refers to a public official acting in relation to the selection process or contract execution. In this context “public official” includes World Bank staff and employees of other organizations taking or reviewing selection decisions. [↑](#footnote-ref-8)
9. For the purpose of this sub-paragraph, “party” refers to a public official; the terms “benefit” and “obligation” relate to the selection process or contract execution; and the “act or omission” is intended to influence the selection process or contract execution. [↑](#footnote-ref-9)
10. For the purpose of this sub-paragraph, “parties” refers to participants in the procurement or selection process (including public officials) attempting either themselves, or through another person or entity not participating in the procurement or selection process, to simulate competition or to establish prices at artificial, non-competitive levels, or are privy to each other’s bid prices or other conditions. [↑](#footnote-ref-10)
11. For the purpose of this sub-paragraph, “party” refers to a participant in the selection process or contract execution. [↑](#footnote-ref-11)
12. A firm or an individual may be declared ineligible to be awarded a Bank-financed contract upon (i) completion of the Bank’s sanctions proceedings as per its sanctions procedures, including inter alia: cross-debarment as agreed with other International Financial Institutions, including Multilateral Development Banks, and through the application of the World Bank Group corporate administrative procurement sanctions procedures for fraud and corruption; and (ii) as a result of temporary suspension or early temporary suspension in connection with an ongoing sanctions proceedings. See footnote 12 and paragraph 8 of Appendix 1 of these Guidelines. [↑](#footnote-ref-12)
13. A nominated sub-consultant, supplier, or service provider is one which has been either (i) included by the consultant in its proposal because it brings specific and critical experience and know-how that are accounted for in the technical evaluation of the consultant’s proposal for the particular services; or (ii) appointed by the Borrower. [↑](#footnote-ref-13)